Rakhine WASH Cluster

MoM Rakhine WASH Cluster Meeting

Date:   	13/11/2015

Venue: 	UNICEF

Time: 	10.00 – 12.00

Chair: 	Rakhine WASH cluster coordinator

Attendees:

| Name | Designation | Organization | Email Address |
| --- | --- | --- | --- |
| George van Vulpen | PHE Coordinator | Oxfam | gvanvulpen@oxfam.org.au |
| Olivier Hariot | WASH PM | SI | sit.watsan@solidarites-myanmar.org |
| Lae Yee Win | WASH Cluster | UNICEF | pannlaephyu7@gmail.com |
| Ewinur Machdar | WASH | UNICEF | ecmachdar@unicef.org |
| Helen Salvestrin | WASH Cluster Co | UNICEF | hesalvestrin@unicef.org |
| Joshua Wilkie | WASH PM | RI | Joshua.wilkie@ri.org |
| Malgonata Kurkowska | RTD WASH PM | SI | rtd.act.manager@solidarites-myanmar.org |
| Frederic Beal | WASH PM | ACF | wash-emergency@mm.missions-acf.org |
| Krishnan Nair | Head of Office | DRC | Krishnan.james.nair@drcmm.org |
| Ngi Ngi Thit | WASH Specialist | Plan International | ngingithit27@gmail.com |
| Aung Min Oo | WASH PM | ACTED | aungminoo.uch@gmail.com |
| Boyet Tiangco | Site Engineer | UNHCR | tiangco@unhcr.org |
| Lei Yee Nway | WASH Consultant | UNICEF | Leeyeenway.myanmar@gmail.com |
| Allison Gocotano | Health Cluster | WHO | gocotanoa@who.int |
| Zaw Min Htet | FCO | OCHA | htet1@un.org |

Apologies: ICRC, IRC, SCI

Agenda:

| Sr. | Topic | Who |
| --- | --- | --- |
|  | Action points from last meeting | WASH cluster |
|  | Returns/relocation/shelter repair update | Shelter cluster |
|  | Disease surveillance | Health cluster |
|  | Latrine working group update | Solidarites |
|  | 2016 WASH strategy | WASH cluster |
|  | AOB | All |

Minutes:

| Topic 1: Action points from last meeting |
| --- |
| Action points | WASH cluster to contact Handicap International in Yangon and request guidelines/ recommendations/other Myanmar-appropriate technology for latrines in camps for persons with specific needs [ongoing] SCi to confirm date for final HP TWG [ongoing] WASH cluster actors to meet on November 18, 09:00, to collaborate on hygiene kit distribution strategy. WASH cluster to subsequently meet with NFI/Food/Protection/CCCM for coordination of strategy and implementation approach. WASH cluster to consolidate rates for incentive/volunteer/outreach workers and CFW (ACTED, IRC, RI) and re-visit in next cluster meeting Township profile updates requested by end of November; RI to update Myebon; IRC to update Ponnagyun and Rathedaung profiles; Malteser to lead update for Maungdaw and Buthidaung. Request for information from Minister of Transport regarding timing of relocations; and status of camp land in 2016 with regards to compensation payment; if compensation payments will not continue, is there a need for WASH agencies to decommission infrastructure (eg STS, latrines). |
| Topic 2: Returns/relocation/shelter repair update |
|  | Six phases for returns/relocations are planned by RSG, as per the attached spreadsheet provided by Shelter cluster. Only 24 shelters (shelter plus latrine) remain to be finalised in Phase 1 (Kyauktaw). Phase 2 includes one village in Kyauktaw and two villages in Mrauk-U; no timeframe has been provided by GAD. Nidin is on hold as IDP community has not agreed to the site. Progress on repairs/rehabilitation for shelters are summarised in attached spreadsheet, as provided by Shelter cluster. |
| Action points |  |
| Topic 3: Disease surveillance |
|  | Health cluster provided the following information on disease surveillance: Surveillance information from rapid response teams are submitted via daily report form to the Strategic Health Operating Center (SHOC) room within the State Health Department. It is then compiled weekly and shared to partners. Data can also be analysed at the camp level. An early warning system with specific case definitions and reporting thresholds is also being discussed at national level. WASH partners query the level and significance of under-reporting of diarrhoeal diseases. Health cluster notes that case definition, reporting threshold, and epidemiologic baseline all needs to be clarified and/or established. WASH partners note that a significant population consult in-camp “medicine-sellers” for diagnosis and treatment, which are not included in camp health statistics. State Health department, Department of Education, and cluster partners have initiated the Communication for Development (C4D) technical working group, which will undertake a state-wide KAP under UNICEF and will subsequently develop IEC materials. Demographic and Health survey for Myanmar is on-going, supported by USAID. Preliminary results expected by mid-2016. WASH and Health cluster coordinators are reviewing existing collaborations, including the draft AWD plan dated March 2015, which will then be open to all agency partners for inputs and finalization. |
| Action points | WASH cluster to provide weekly health data from Health cluster. Request to Health cluster to release KAP results to WASH cluster when complete. Health sector to confirm barriers to clinics being open beyond the existing 09:00 – 14:00 schedule; and barriers to static clinics in camps. |
| Topic 4: Latrine TWG update |
|  | Solidarites provided an update on latrine technical working group which reviewed lessons learned, best practices and recommended improvements on all elements of sanitation in Sittwe IDP camps including latrine pit and superstructure to desludging, sewage treatment and cross cutting issues, as per attached presentation. One more TWG session will be held at the end of November to share final guidance notes; date to be confirmed by SI. |
| Action points | SI to confirm date and facilitate final TWG for latrines Working group/cluster to update existing guidance note with outcomes |
| Topic 5: 2016 Rakhine WASH cluster strategy planning workshop |
|  | Agencies tentatively agreed on 14/15 January for the Rakhine WASH cluster strategy planning workshop. WASH agencies suggested the following topics for the 2016 workshop: Community and CMC ownership and management of latrines/water points/drainage, noting major protection issues associated with CMC control of camp services (food, shelter, NFI etc) Ending displacement/durable solutions/exist strategy to early recovery focusing on the Sittwe majority Expanding health/nutrition and WASH links Groundwater potential for water supply based on the ongoing research of Hydrogeologists Without Borders Ceramic Water Filter evaluation and potential other household water treatment options, as required Review of habitat package including O&M for specific locations, considering minimizing pollution points |
| Action points | WASH cluster to finalise and distribute invitation and agenda to WASH strategy workshop |
| Topic 6: AOB |
|  | Agencies request support in addressing unofficial payments for additional WASH infrastructure (replacement latrines, new sewage treatment sites etc) and mismanagement of camp infrastructure by CMC in camps |
| Action points | WASH cluster to request support from ICCG to address ongoing requests for unofficial payments and mismanagement of camp infrastructure. |

Next meeting: Friday, 27 November 2015, 10:00 – 12:00, with DRD/Minister of Transport at RSG