## EPW_AP
RAKHINE STATE |  |  | Amended
Emergency Preparedness Working Group ( OCHA Lead) Action Points Follow-up |  |  | Closed
Updated 24 February 2016 |  |  | Completed
Ongoing
Pending
Action | Forum | Responsible Actors | Start date | Timeframe/ deadline | Update | Original_Status | Status
Protection sector updated stock availability (such as contact list, tools, service mapping, SOP) and share to OCHA | EPWG | Protection sector |  | 2016-02-26 |  |  | Pending
Food security sector updated the contact list | EPWG | Food security sector |  | 2016-02-29 |  |  | Pending
Protection sector revised update and share all related documents | EPWG | Protection sector |  | 2016-03-11 |  |  | Pending
Sector/cluster should be able to articulate coordination staffs for natural disaster response | EPWG | Sector/cluster | 2016-02-18 | 2016-03-15 |  |  | Pending
Sector/cluster coordinators need to identify township coordination necessary for each respective sector | EPWG | Sector/cluster | 2016-02-18 | 2016-03-15 |  |  | Pending
OCHA organize to national organization to develop the preparedness workshop to identify their capacity and coordination way forward. | EPWG | OCHA | 2016-02-24 | 2016-03-15 | Workshop planned for the 11 March |  | Ongoing
International organizations & National organization workshop (OCHA Chair) to ensure coordination during emergencies | EPWG | OCHA | 2016-02-24 | 2016-03-21 | date to agree on week starting 14/03 |  | Pending
Sector/Cluster coordinators to ensure that the updated MIRA formats is endorsed by their correspondent coordinator in Yangon | EPWG | Sector/cluster |  | 2016-03-21 |  |  | Pending
Sector/cluster lead to send contacts of local key informants from state to village level to OCHA | EPWG | Sector/cluster | 2016-02-18 | 2016-03-15 |  |  | Pending
Establishment Preparedness meeting EAHCT | EPWG | OCHA |  | 2016-03-30 |  |  | Pending
DRR group should to coordinate with RSG on evacuation plan and share with OCHA and sector/cluster coordinators. | EPWG | DRR group /IOM |  | 2016-03-15 |  |  | Pending
Security should be planned for organization evacuation/reallocation plan (staff, essential staff, asset, relocation). OCHA to contact UNDSS and EAHCT | EPWG | OCHA |  | 2016-03-31 |  |  | Pending
Food security sector updated stock and selected focal points for assessment | EPWG | Food security sector |  | 2016-03-31 |  |  | Pending
Sector/cluster will review list operational considerations, to define EAHCT, coordination arrangement at District/Township Level, additional operational SOPs/to define caseloads and update list of stocks and staffs | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
Relationship with CSO and private sector in collective shelters and capacity before the next cyclone season | EPWG | Shelter cluster |  | 2016-03-30 |  |  | Pending
Training for other sector staffs for protection mainstreaming | EPWG | Protection sector |  | 2016-04-01 |  |  | Pending
Reporting formats | EPWG | OCHA |  | 2016-03-20 |  |  | Pending
OCHA to update 3 W and Google earth base map | EPWG | OCHA |  | 2016-03-20 |  |  | Pending
Cluster/sector to updated list of stocks and of logistic capacity | EPW | Sector/cluster |  | 2016-03-15 |  |  | Pending
Vulnerability mapping such as tidal surge/flood prone areas. | EPW | OCHA |  | 2016-03-15 |  |  | Pending
MOUs/TAs fast track procedure to be identified with RSG and Union | EPWG | OCHA |  | 2016-03-31 |  |  | Pending
Manageable caseload, surge requirement, threshold | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Education and CCCM/Shelter to consolidate data on schools | EPWG | Shelter/Education |  | 2016-03-15 |  |  | Pending
Emergency response training by sector/cluster to respective partners | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
Sector/cluster to identify assessment team sent to OCHA | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Logistic capacity assessment | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
WFP to provide information on transport network for emergency response | EPWG | WFP |  | 2016-03-31 |  |  | Pending
Civil-military coordination important to identify way forward in preparation for natural disaster response. Yangon leading | EPWG | OCHA |  | 2016-03-31 |  |  | Pending
Sector/cluster to updated the government counterpart contact list and sent to OCHA | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
Cluster reviewed the respective MPAs/APAs and SOP | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Cluster/sector to identify sector coordination at different administrative level | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Cluster/sector to identify IM capacity and needs | EPWG | OCHA |  |  |  |  | Pending
UNHCR to clarify their role in case of emergency as Shelter/protection/cccm/NFI sector/cluster coordinator | EPWG | UNHCR |  | 2016-03-15 |  |  | Pending
UNHCR to clarify their role in case of emergency as general coordinator for Maungdaw and Boutidong | EPWG | UNHCR |  | 2016-03-15 |  |  | Pending
FP of EPWS working group to share their notes with OCHA | EPWG | OCHA |  | 2016-03-15 |  |  | Pending
Cluster/sector to send MPA, APA and SOP for emergency response | EPWG | Sector/cluster |  | 2016-03-15
Partners and sector/cluster to provide in put for INGO/UN/NNGO workshop | EPWG | All |  | 2016-03-15
Assessment trainig workshop for assessment teams | EPWG | OCHA |  | 2016-03-31

## AHCT
Forum | AHCT Rakhine
Column Labels
| Completed | Ongoing | (blank) | Pending | Closed | Amended | Grand Total | Completed | Ongoing | Nil | Pending | Closed | Amended
Count of Action | 44 | 4 | 1 | 6 | 8 | 1 | 64 | 44 | 4 | 1 | 6 | 8 | 1
Amended
Closed
Completed
Ongoing
Pending
Forum | AHCT Rakhine
Count of Action | Status
Responsible Actors | Completed | Ongoing | (blank) | Pending | Closed | Amended | Grand Total | Agency | OCHA action point Total | Completed | Ongoing | Pending | Closed | Amended
AHCT | 2 | [5 empty] | 2 | OCHA | 29 | 25 | 0 | 1 | 2 | 1
AHCT members | 3 |  | 1 | 2 | 2 |  | 8
AHCT/ICCG |  |  |  |  | 1 |  | 1
All agencies | 1 | [5 empty] | 1
Cluster/Sector | 3 | [5 empty] | 3
FSW/PWG | 1 | [5 empty] | 1
INGO | 1 | 1 |  |  |  |  | 2
OCHA | 25 |  |  | 1 | 2 | 1 | 29
OCHA, Food, CCCM and PWG |  |  |  | 1 |  |  | 1
PWG |  |  |  |  | 1 |  | 1
PWG/FSS | 1 | [5 empty] | 1
RCO,UNHCR, OCHA |  |  |  | 1 |  |  | 1
UNDP | 3 |  |  |  | 2 |  | 5
UNDSS | 1 | [5 empty] | 1
UNHCR | 1 | 1 |  | 1 |  |  | 3
UNICEF, UNHCR, OCHA and one INGO | 1 | [5 empty] | 1
UNICEF/Partners |  | 1 |  |  |  |  | 1
WFP | 1 | 1 |  |  |  |  | 2
Grand Total | 44 | 4 | 1 | 6 | 8 | 1 | 64
Forum | AHCT Rakhine
Status | Ongoing |  | Status | Ongoing
AHCT meeting's Ongoing action points as of 31 Dec 2015 |  |  | AHCT meeting's Ongoing action points as of 31 Dec 2015
Responsible Actors | Action |  | Responsible Actors | Count of Action |  | Responsible Actors | Count of Action
INGO | INGOs to inform OCHA the replacement of outgoing INGO AHCT representatives |  | INGO | 1 |  | Ongoing AP Total | 4
UNHCR | UNHCR to follow up government head count exercise |  | UNHCR | 1 |  | INGO | 1
UNICEF/Partners | UNICEF and concerned partners to convene a meeting with OCHA to seek way forward on access issues |  | UNICEF/Partners | 1 |  | UNHCR | 1
WFP | WFP to share beneficiary priortization guideline for consultation with AHCT |  | WFP | 1 |  | UNICEF/Partners | 1
|  |  | Grand Total | 4 |  | WFP | 1
Forum | AHCT Rakhine |  | Forum | AHCT Rakhine
Status | Pending |  | Status | Pending
AHCT meeting's Pending action points 31 Dec 2015 |  |  | AHCT meeting's Pending action points 31 Dec 2015
Responsible Actors | Action |  | Responsible Actors | Count of Action |  | Responsible Actors | Count of Action
AHCT members | AHCT members to provide inputs for presentation to CSOs/NNGOs by next AHCT |  | AHCT members | 2 |  | Pending AP Total | 6
| AHCT members to provide list of data entry clerk from agencies to OCHA |  | OCHA | 1 |  | AHCT members | 2
OCHA | OCHA to share a draft presentation for information session. |  | OCHA, Food, CCCM and PWG | 1 |  | OCHA | 1
OCHA, Food, CCCM and PWG | Meeting on CwC works among Food, CCCM and Protection to be organized |  | RCO,UNHCR, OCHA | 1 |  | OCHA, Food, CCCM and PWG | 1
RCO,UNHCR, OCHA | Chris Carter, OCHA and UNHCR to propose RSG with the plan |  | UNHCR | 1 |  | RCO,UNHCR, OCHA | 1
UNHCR | UNHCR to develop disclaimer message for data digitalization assistance to RSG |  | Grand Total | 6 |  | UNHCR | 1
Forum | AHCT Rakhine |  | Forum | AHCT Rakhine
Status | Closed |  | Status | Closed
AHCT meeting's Closed action points as of 31 Dec 2015 |  |  | AHCT meeting's Closed action points as of 31 Dec 2015
Responsible Actors | Action |  | Responsible Actors | Count of Action |  | Responsible Actors | Count of Action
AHCT members | AHCT participants to send the map of RAP plan back to OCHA |  | AHCT members | 2 |  | Closed AP Total | 8
| Partners to send OCHA available assessments on context analysis |  | AHCT/ICCG | 1 |  | AHCT members | 2
AHCT/ICCG | AHCT to develop guidance types of intervention based on needs. |  | OCHA | 2 |  | AHCT/ICCG | 1
OCHA | OCHA to organize facilitator and provide background documentation for the session on RAP |  | PWG | 1 |  | OCHA | 2
| OCHA to seek clarity on the transition of Conflict Management Center with RSG |  | UNDP | 2 |  | PWG | 1
PWG | PWG to look at protection risk for returnees (Bangladesh) |  | Grand Total | 8 |  | UNDP | 2
UNDP | UNDP to circulate matrix for inputs by sector/cluster on ER Network
UNDP to update on ER progress and support to return project
Forum | AHCT Rakhine |  | Forum | AHCT Rakhine
Status | Amended |  | Status | Amended
AHCT meeting's Amened action points as of 31 Dec 2015 |  |  | AHCT meeting's Amened action points as of 31 Dec 2015
Responsible Actors | Action |  | Responsible Actors | Count of Action |  | Responsible Actors | Count of Action
OCHA | OCHA to re-circulate draft on priority areas for recommendation to HCT |  | OCHA | 1 |  | Amended AP Total | 1
|  |  | Grand Total | 1 |  | OCHA | 1

## Status
Status
Amended
Closed
Completed
Ongoing
Pending