## EPW_AP
RAKHINE STATE |  |  | Amended
Emergency Preparedness Working Group ( OCHA Lead) Action Points Follow-up |  |  | Closed
Updated 24 February 2016 |  |  | Completed
Ongoing
Pending
Action | Forum | Responsible Actors | Start date | Timeframe/ deadline | Update | Original_Status | Status
Protection sector updated stock availability (such as contact list, tools, service mapping, SOP) and share to OCHA | EPWG | Protection sector |  | 2016-02-26 |  |  | Pending
Food security sector updated the contact list | EPWG | Food security sector |  | 2016-02-29 |  |  | Pending
Protection sector revised update and share all related documents | EPWG | Protection sector |  | 2016-03-11 |  |  | Pending
Sector/cluster should be able to articulate coordination staffs for natural disaster response | EPWG | Sector/cluster | 2016-02-18 | 2016-03-15 |  |  | Pending
Sector/cluster coordinators need to identify township coordination necessary for each respective sector | EPWG | Sector/cluster | 2016-02-18 | 2016-03-15 |  |  | Pending
OCHA organize to national organization to develop the preparedness workshop to identify their capacity and coordination way forward. | EPWG | OCHA | 2016-02-24 | 2016-03-15 | Workshop planned for the 11 March |  | Ongoing
International organizations & National organization workshop (OCHA Chair) to ensure coordination during emergencies | EPWG | OCHA | 2016-02-24 | 2016-03-21 | date to agree on week starting 14/03 |  | Pending
Sector/Cluster coordinators to ensure that the updated MIRA formats is endorsed by their correspondent coordinator in Yangon | EPWG | Sector/cluster |  | 2016-03-21 |  |  | Pending
Sector/cluster lead to send contacts of local key informants from state to village level to OCHA | EPWG | Sector/cluster | 2016-02-18 | 2016-03-15 |  |  | Pending
Establishment Preparedness meeting EAHCT | EPWG | OCHA |  | 2016-03-30 |  |  | Pending
DRR group should to coordinate with RSG on evacuation plan and share with OCHA and sector/cluster coordinators. | EPWG | DRR group /IOM |  | 2016-03-15 |  |  | Pending
Security should be planned for organization evacuation/reallocation plan (staff, essential staff, asset, relocation). OCHA to contact UNDSS and EAHCT | EPWG | OCHA |  | 2016-03-31 |  |  | Pending
Food security sector updated stock and selected focal points for assessment | EPWG | Food security sector |  | 2016-03-31 |  |  | Pending
Sector/cluster will review list operational considerations, to define EAHCT, coordination arrangement at District/Township Level, additional operational SOPs/to define caseloads and update list of stocks and staffs | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
Relationship with CSO and private sector in collective shelters and capacity before the next cyclone season | EPWG | Shelter cluster |  | 2016-03-30 |  |  | Pending
Training for other sector staffs for protection mainstreaming | EPWG | Protection sector |  | 2016-04-01 |  |  | Pending
Reporting formats | EPWG | OCHA |  | 2016-03-20 |  |  | Pending
OCHA to update 3 W and Google earth base map | EPWG | OCHA |  | 2016-03-20 |  |  | Pending
Cluster/sector to updated list of stocks and of logistic capacity | EPW | Sector/cluster |  | 2016-03-15 |  |  | Pending
Vulnerability mapping such as tidal surge/flood prone areas. | EPW | OCHA |  | 2016-03-15 |  |  | Pending
MOUs/TAs fast track procedure to be identified with RSG and Union | EPWG | OCHA |  | 2016-03-31 |  |  | Pending
Manageable caseload, surge requirement, threshold | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Education and CCCM/Shelter to consolidate data on schools | EPWG | Shelter/Education |  | 2016-03-15 |  |  | Pending
Emergency response training by sector/cluster to respective partners | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
Sector/cluster to identify assessment team sent to OCHA | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Logistic capacity assessment | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
WFP to provide information on transport network for emergency response | EPWG | WFP |  | 2016-03-31 |  |  | Pending
Civil-military coordination important to identify way forward in preparation for natural disaster response. Yangon leading | EPWG | OCHA |  | 2016-03-31 |  |  | Pending
Sector/cluster to updated the government counterpart contact list and sent to OCHA | EPWG | Sector/cluster |  | 2016-03-31 |  |  | Pending
Cluster reviewed the respective MPAs/APAs and SOP | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Cluster/sector to identify sector coordination at different administrative level | EPWG | Sector/cluster |  | 2016-03-15 |  |  | Pending
Cluster/sector to identify IM capacity and needs | EPWG | OCHA |  |  |  |  | Pending
UNHCR to clarify their role in case of emergency as Shelter/protection/cccm/NFI sector/cluster coordinator | EPWG | UNHCR |  | 2016-03-15 |  |  | Pending
UNHCR to clarify their role in case of emergency as general coordinator for Maungdaw and Boutidong | EPWG | UNHCR |  | 2016-03-15 |  |  | Pending
FP of EPWS working group to share their notes with OCHA | EPWG | OCHA |  | 2016-03-15 |  |  | Pending
Cluster/sector to send MPA, APA and SOP for emergency response | EPWG | Sector/cluster |  | 2016-03-15
Partners and sector/cluster to provide in put for INGO/UN/NNGO workshop | EPWG | All |  | 2016-03-15
Assessment trainig workshop for assessment teams | EPWG | OCHA |  | 2016-03-31

## AHCT
Forum | - all -
Status
Ongoing | (empty) | Pending | Total Result |  |  |  | Completed | Ongoing | Nil | Pending | Closed | Amended
1 | 3 | 34 | 38 |  |  |  | 44 | 4 | 1 | 6 | 8 | 1
Amended
Closed
Completed
Ongoing
Pending
Forum | - all -
Count of Action | Status
Responsible Actors | Ongoing | (empty) | Pending | Total Result |  |  | Agency | OCHA action point Total | Completed | Ongoing | Pending | Closed | Amended
OCHA | 1 | 1 | 9 | 11 |  |  | OCHA | 29 | 25 | 0 | 1 | 2 | 1
UNHCR |  |  | 2 | 2
WFP |  |  | 1 | 1
All |  | 1 |  | 1
DRR group /IOM |  |  | 1 | 1
Food security sector |  |  | 2 | 2
OCHA |  |  | 1 | 1
Protection sector |  |  | 3 | 3
Sector/cluster |  | 1 | 13 | 14
Shelter cluster |  |  | 1 | 1
Shelter/Education |  |  | 1 | 1
(empty)
Total Result | 1 | 3 | 34 | 38
Forum | - all -
Status | Ongoing |  | Status | Ongoing
Responsible Actors | Action | (empty) | Responsible Actors | Count of Action | Responsible Actors | Count of Action
OCHA | OCHA organize to national organization to develop the preparedness workshop to identify their capacity and coordination way forward. |  | OCHA | 1 | Ongoing AP Total | 4
|  |  | Total Result | 1 | INGO | 1
[5 empty] | UNHCR | 1
[5 empty] | UNICEF/Partners | 1
[5 empty] | WFP | 1
Forum | - all - |  | Forum | - all -
Status | Pending |  | Status | Pending
Responsible Actors | Action | (empty) | Responsible Actors | Count of Action | Responsible Actors | Count of Action
OCHA | FP of EPWS working group to share their notes with OCHA |  | OCHA | 9 | Pending AP Total | 6
| Civil-military coordination important to identify way forward in preparation for natural disaster response. Yangon leading |  | UNHCR | 2 | AHCT members | 2
| Cluster/sector to identify IM capacity and needs |  | WFP | 1 | OCHA | 1
| Establishment Preparedness meeting EAHCT |  | DRR group /IOM | 1 | OCHA, Food, CCCM and PWG | 1
| International organizations & National organization workshop (OCHA Chair) to ensure coordination during emergencies |  | Food security sector | 2 | RCO,UNHCR, OCHA | 1
| MOUs/TAs fast track procedure to be identified with RSG and Union |  | OCHA | 1 | UNHCR | 1
| OCHA to update 3 W and Google earth base map |  | Protection sector | 3
| Reporting formats |  | Sector/cluster | 13
| Vulnerability mapping such as tidal surge/flood prone areas. |  | Shelter cluster | 1
UNHCR | UNHCR to clarify their role in case of emergency as general coordinator for Maungdaw and Boutidong |  | Shelter/Education | 1
| UNHCR to clarify their role in case of emergency as Shelter/protection/cccm/NFI sector/cluster coordinator |  | Total Result | 34
WFP | WFP to provide information on transport network for emergency response
Forum | - all - |  | Forum | - all -
Status | - all - |  | Status | - all -
(empty) |  |  | Count of Action |  | Responsible Actors | Count of Action
[5 empty] | Closed AP Total | 8
[5 empty] | AHCT members | 2
[5 empty] | AHCT/ICCG | 1
[5 empty] | OCHA | 2
[5 empty] | PWG | 1
[5 empty] | UNDP | 2
Manageable caseload, surge requirement, threshold
Sector/cluster coordinators need to identify township coordination necessary for each respective sector
Sector/Cluster coordinators to ensure that the updated MIRA formats is endorsed by their correspondent coordinator in Yangon
Sector/cluster lead to send contacts of local key informants from state to village level to OCHA
Sector/cluster should be able to articulate coordination staffs for natural disaster response
Sector/cluster to identify assessment team sent to OCHA
Forum | - all - |  | Forum | - all -
Status | - all - |  | Status | - all -
(empty) |  |  | Count of Action |  | Responsible Actors | Count of Action
[5 empty] | Amended AP Total | 1
[5 empty] | OCHA | 1

## Status
Status
Amended
Closed
Completed
Ongoing
Pending