Rakhine WASH Cluster

MoM Rakhine WASH Cluster Meeting

Date:   01/042016

Venue: 	UNICEF

Time: 	10.00 – 12.00

Chair: 	Ewinur Machdar Acting Rakhine WASH sub- cluster coordinator

Attendees:

| No | Name | Designation | Organization | Email Address | Contact Phone |
| --- | --- | --- | --- | --- | --- |
| 1 | Thein Tun Hlaing | Info Management | UNICEF | tthlaing@unicef.org | 09 260275056 |
| 2 | Fabuo Borba | SHELTER | LWF | fmpborba@hotmail.com | 09 453050298 |
| 3 | Han Min Htet | WASH/ PC | SCI | hanmin.htet@savethechildren.org | 09 440224018 |
| 4 | Laurei Hanson | Progrogram Development & Reporting | SCI | LAVREIJ.HANSON@savethechildren.org | 09 263358119 |
| 5 | Lai Nge | Senior Engineer | DRC | Lainge@drcmm.org | 09 450543314 |
| 6 | Aung Than | PM | IRC | Aung.Than@rescue.org | 09 450542984 |
| 7 | Rakesh Mohaw | Area Manager | Oxfam | RAMOHAN@oxfam.org.uk | 09 264542915 |
| 8 | MARTINA DI GIULIO | Wathab Delegate | ICRC | mdigiulio@icrc.org | 09 258681243 |
| 9 | Sandra Eigenheer | Wathab Delegate | ICRC | seigenheer@icrc.org | 09 420281442 |
| 10 | Lae Yee Win | WASH Officer | UNICEF | pannlaephyu7@gmail.com | 09 254820143 |

Aapologies: SI

Agenda:

| Sr. | Topic | Who |
| --- | --- | --- |
|  | Action points from last meeting | WASH cluster |
|  | CCCM Reform workshop update | Richard, UNHCR |
|  | Emergency preparedness for next cyclone season | WASH Cluster |
|  | Drought | WASH Cluster |
|  | 4W revamp | WASH cluster |
|  | AOB | All |

Minutes:

| Topic 1: Action points from last meeting |  |
| --- | --- |
| - Contingency stock request to be sent out nationally. Sent to partners for update but only with received only few response, and also most of them have limited supplies - WASH cluster to raise the problem of emergency import clearances to ICCG. Pending, National WASH Cluster will raise this into national ICCG. |  |
| Outstanding actions |  |
| Topic 2: CCCM reform |  |
| RSG and CCCM partners held a workshop on Friday 25th March to discuss the options for reforming camp management committees. This was a government leads process where CCCM cluster provided options to improve CMC performance with proposing clear roles and responsibility. Report is still under development and need to be endorsed by RSG before it become public. |  |
| Action points | - CCCM Cluster to update the process and share the report to WASH cluster |
| Topic 3: Emergency preparedness for next cyclone season |  |
| OCHA held a preparedness workshop for partners (international NGO and local CSOs) to improve emergency response and assessment for next cyclone season. Two days assessment training also conducted for assessment to familiarize with new MIRA form and KOBO (digital data collection). WASH caseload developed to identify threshold and activation of surge support. |  |
| Action points | - To share WASH preparedness document (APA, MPA and caseload, ERPP Myanmar 2015) |
| Topic 4: Drought |  |
| DRD has identified villages that affected by drought, divided per time line (priority 1: dried in March-April; priority 2: dried in April – May; priority 3: dried in May – June). Response has been implemented in several villages that been dried in March. DRD propose Union government to support, however due to transition there is no confirmation to date. Partners that planned to intervene, has to coordinate and discuss with township DRD. ICRC is on standby to support Mrauk U and Kyauk Taw area. They have capacity to support 1000 tarpaulins tanks, water tankering and water treatment (if it needed) IRC is on standby to support Rathedaung and Ponnagyun with water tankering and biosand filter (if it needed) UNICEF has some tarpaulins that could be used for water storage if it needed. |  |
| Action points | - To share DRD drought response plan - Partners could collect township DRD drought maps with flashdrive to WASH cluster - DRD contact list |
| Topic 4: 4W revamp |  |
| 4W recognised as being outdated and not reflecting true gaps associated with WASH infrastructures. Key challenges are monitoring functionality of latrine superstructures, desludging and overall costs of O&M. As current 4W is covering all, new proposal is to separate between displacement response with villages and emergency (natural disaster). Number of indicators would also be reduce and thus cluster needs input from all partners. Based on last discussion with National cluster, there are some indicators to be included in the new 4W (see attached). Feedback should be submitted to WASH Cluster by Friday 22 April by email and followed by 1 day workshop to finalize and to have consensus. |  |
| Action points | - WASH Cluster to share proposed indicators for new 4W - All partners expected to provide feedback by 21 April and followed by workshop by 27 April for consensus. |
| Topic 5: AOB |  |
|  | UNHCR – protection (Stefan) : UNHCR is organizing a HLP (Housing, Land and Property) workshop, facilitated by an expert with a lot of experience in Myanmar.HLP issues are of increasing importance not only to protection actors, when discussing returns or other solutions, but to most other clusters/sectors/agencies with field implementation. Workshop will be held on 7 April 2016 at OCHA and strongly recommended for WASH partners to participated |
| Action points |  |

Next meeting: Friday 29 April 2016