Rakhine WASH Cluster

Agenda for Rakhine WASH Cluster Meeting

Date:   	06/03/2017

Venue: 	UNICEF office

Time: 	10:00h ~ 12:00h

Duration: 	2 hrs

Chair:		Rakhine WASH Cluster

Attendees:

| No | Name | Designation | Organization | Email | Phone |
| --- | --- | --- | --- | --- | --- |
| 1 | Zaw Myo Wai | Technical Expert | GIZ |  | 09450542782 |
| 2 | Myint Zu Soe | Technical Expert | GIZ |  | 09794843135 |
| 3 | Dr. Zaw Khant | Team Leader | MHDO |  | 095167258 |
| 4 | Zin Mee Lwin | Engineer | MHDO |  | 09422460732 |
| 5 | LEWIS SIDA | Advisor | DEFID-HARP |  | 09768160649 |
| 6 | Aung Min Oo | WASH PM | RI | aung.minoo@ri.org | 09451978021 |
| 7 | Nyi Nyi Thit | WASH Officer | UNICEF | nthit@unicef.org | 09421733834 |
| 8 | NIC Pyatt | Programme Quality Morning | HARP | nic.pyatt@harpfacility.org | 09420276994 |
| 9 | Melvin Tebbutt | HARP | HARP | melvin.tebbutt@harpfacility.org | 09762492716 |
| 10 | Brice | WASH PM | SI | sit.watsan@solidarities-myanmar.org | 09-420070354 |
| 11 | Richard Ellert | Consultant | GIZ | ellert@ellertnet.de | 09423114575 |
| 12 | Stephan FAYON | Agri | GIZ | stephan8@aurorille.org.in | 09453491192 |
| 13 | Bagus | PHE | Oxfam | bgetyawan@oxfam.org.uk |  |
| 14 | Kyaw Thet | WASH Officer | UNICEF | kthet@unicef.org |  |
| 15 | Thaw Si Htin Zaw | WASH PM | SCI | Thawsihtin.zaw@savethechildren.org | 09456250150 |
| 16 | Wint Wah Htay | WASH PC | SCI | wintwar.htay@savethechildren.org | 09422489527 |
| 17 | Kris Cahyanto | WASH Cluster Coordinator | UNICEF/ Cluster | bkcahyanto@unicef.org |  |

Agenda:

| Sr. | Topic | Time | Who |
| --- | --- | --- | --- |
| 1. | Self-Introduction | 5 min | All Participants |
| 2. | Review action points from previous meeting minutes | 5 min | Kris |
| 3. | 4Ws update for 1st Quarter 2017 | 15 min | Kris |
| 4. | WASH Contingency Plan for 2017 | 5 min | Kris |
| 5. | Introduction for HARP facility | 15 min | DEFID |
| 6. | Update from NRS | 10 min | All Participants |
| 7. | UNHCR Protection & WASH | 15 min | UNHCR |
| 8 | CCCM Camp Profiling | 15 min | UNHCR |
| 9 | Update on WASH Hygiene Kit Strategy TWG | 10 min | All Participants |
| 10 | Update from meeting/ field visit with DC/TA on WASH issues and CMC issues in Sittwe | 5 min | All Participants |
| 11 | Coordination Mechanism with Government Focal Point | 10 min | All Participants |
| 12 | AOB | 10 min | All Participants |

Minutes:

| Topic 1: Review action points from previous meeting minutes |  |
| --- | --- |
| Summary of discussion | - HK TWG to continue the next discussion on the detail of focus group discussion for PDM monitoring - The agencies which have not been sent the updates on WASH situation analysis to send to WASH Cluster. - WASH agencies to facilitate and support HARF facility in the process - CCCM cluster to follow up with CCCM Cluster Co., and the government officials on the dissemination of SOP issue to the CMC. - Possible duplication of WASH supplies and NFI kits; WASH Cluster to follow up - WASH cluster to gather data on WASH support and response. - CCCM and WASH Cluster to share the update contact list of government State focal points. |
| Action plan | - HK TWG to continue the next discussion on the detail of focus group discussion for PDM monitoring - Possible duplication of WASH supplies and NFI kits; WASH Cluster to follow up with other sectors/ Clusters |
| Topic 2: 4Ws update for 1st Quarter 2017 |  |
| Summary of discussion | - WASH IM will be visiting to Sittwe in the next 2 weeks to guide the WASH agencies to fill in the new WASH 4Ws with small modification/adjustment to represent the existing situation in the camp. |
| Action Plan | - Revision on WASH 4Ws will be made to accommodate current WASH services in the camp. - WASH IM will arrive on 23 March 2017 and will organize short training with WASH Agencies IM staffs - New WASH Sub Cluster Coordinator will arrive on 4th week of March and will follow up about new 4 Ws finalize update - Submission of WASH 4Ws and collection by WASH IM |
| Topic 3: WASH Contingency Plan for 2017 |  |
| Summary of discussion | - WASH Agencies need to share their stock list and Contingency plan for 2017 |
| Action Plan | - WASH Cluster Officer will collect the data from WASH Agencies. |
| Topic 4. Introduction for HARP facility & GIZ |  |
| Summary of discussion | - HARP – F will be taken the responsibilities of Humanitarian needs and Gaps what opportunity it is for Funding resources and technical support in 3 or 4 years funding. HARP will be providing support for WASH services in Camps and NRS. - GIZ is the development agencies for 3 years programme in Rakhine and will be organize local NGO to development for feasibility of sanitation facilities, Nutrition & WASH and health centers construction in two townships, Kyauktaw and Pauktaw. |
| Action Plan | - HARP is compiling WASH activities in Camp for long term planning. - GIZ: WASH Agencies who are interested to work on WASH/Nutrition development activities to contact GIZ. |
| Topic 5: Update from NRS |  |
| Summary Discussion | - WASH HK distributed conducted by some WASH agencies, such as Malteser/ Mercy Malaysia, CCCM/NFI, Care, ACF and UNICEF - Impact WASH Analysis |
| Action Points | - WASH agencies to submit their reports to UNCHR in NRS |
| Topic 6: Update on WASH Hygiene Kit Strategy TWG |  |
| Summary Discussion | - WASH Hygiene Kit Strategy TWG finalized first step as two PDM formats, Hygiene kit tools and PDM tools. Bigger one will be updated in every six month. It is link with all the market price’s increase in the camp. - For Hygiene kit distribution, standard price per kit is 4000 MMK. - Second step is ongoing for FGD format and questionnaires of mensural hygiene management for women is not finished yet. |
| Action Points | - TWG will share two formats with COBO data base to WASH Cluster with English and Myanmar translation. |
| Topic 7: Update from meeting/ field visit with DC/TA on WASH issues and CMC issues in Camps |  |
| Summary Discussion | - TA visited to the camps with WASH Agencies, SCI and OXFAM, and discussed with CMC and land owners about land issues, Labor issues and block activities by Land owners and CMA. - SCI Visited to Sin Tet Maw Camp, they found that new shelter construction is ongoing by UNHCR. WASH PM from SCI reported 15 shelters constructed in the same place and Contractor didn’t take care about the existing bathing facilities slab (2’ x 2’) and moved away from Shelter rooms. SCI did not receive any information from CMA and UNHCR. - WASH Cluster did not receive any information about reconstruction plan from CMA and Shelter Cluster. - This is not first time for WASH Agencies because of all of the water points were removed for reconstruction of Shelters in Baw Du Pha Camp last year. - The main issues are only contractor works on the ground level for shelter construction and agencies shelter staffs cannot monitor and they did not think about the linkage between CCCM, Shelter and WASH. - CMA focused on Shelter Cluster work and did not coordinate with WASH agencies and did not share about where will be built?, how they will implement and their plan too |
| Action Points | - ODG (N) and STMG Camp issues were solved by TA, WASH Agencies and WASH Cluster. - WASH Cluster Coordinator will raise CMA issues related with Shelter construction to Nation Level - SI won’t be responsibilities for current government latrine construction design, desludging and O&M in future in Dar Pai Camp. - SCI will send official e mail to UNHCR about STM Shelter construction and without common understanding between us and WASH Cluster Coordinator will be follow up on that issue and highlight to CMA. |
| Topic 8: Coordination Mechanism with Government Focal Point |  |
| Summary Discussion | - WASH Agencies should send proposed letter to Chief Minister or State Secretory and Cc to District Commissioner and Township Administrator. |
| Action Points | - WASH Cluster need to follow up WASH issues with different levels of government not to delay and block information between RSG and GAD Township level. |
| Topic 9: AOB |  |
| Summary Discussion | - Oxfam market assessment training will be conducted on 15 March, 2017 - Oxfam Tiger Worm Toilet Group will monitor in Say Tha Ma Gyi Camp. - Next WASH Cluster Meeting will be held on 24 March 2017. |
| Action Points | - WASH Agencies will be compiling Training plan for 2017. |