Rakhine WASH Cluster

Agenda for Rakhine WASH Cluster Meeting

Date:   	17/02/2017

Venue: 	UNICEF office

Time: 	10:00h ~ 12:00h

Duration: 	2 hrs

Chair:		Rakhine WASH Cluster

Attendees:

| No | Name | Designation | Organization | Email | Phone |
| --- | --- | --- | --- | --- | --- |
| 1 | Zaw Min Tun | WASH Team Leader | CDN | washtl.sittwe@cdnmyanmar.org | 09250591043 |
| 2 | Dereje Den | WASH SPM | SCI | Dereje.deneke@savethechildren.org | 09454292220 |
| 3 | Kyaw Kyaw San | FA (CCCM) | UNHCR | sank@unhcr.org | 09421053662 |
| 4 | Hay Mar | FA (CCCM) | UNHCR | waihnin@unhacr.org | 09421732845 |
| 5 | Nicolas Guillaud | Consortia Manager | SCI | nicolas.guillaud@savethechildren.org | 0943042814 |
| 6 | Melvin Tebbutt | HARP | MA-UK | Melvin.tebbutt@harpfacility.org | 09262692716 |
| 7 | Thaw Si Htin Zaw | WASH PM | SCI | Thawsihtin.zaw@savethechildren.org | 09456250150 |
| 8 | Nadime Eriksson | PC | Medair | Pc-mmr.org@medair.org | 09265382876 |
| 9 | Anna Trzcinska | WASH PM | RI | Anna.trzcinska@ri.org | 09458371388 |
| 10 | Daw Naing Soe Aye | Laison Officer | UNOPS | naingsoea@unops.org | 09254337285 |
| 11 | Aung Min Oo | WASH PM | RI | Aung.minoo@ri.org | 09451978021 |
| 12 | Bagus | PHE | Oxfam |  |  |
| 13 | Moneth | PHP | Oxfam | msolleza@oxfam.org.uk |  |
| 14 | Stephanie Tam | WASH Coordinator | DRC | Stephanie.tam@drcmm.org | 09451928852 |
| 15 | Kris Cahyanto | WASH Cluster Coordinator | UNICEF/ Cluster | bkcahyanto@unicef.org |  |
| 16 | Lei Yee Nway | WASH Officer | UNICEF | lnway@unicef.org | 09450015864 |
| 17 | Lae Yee Win | WASH Officer | UNICEF | laewin@unicef.org | 09254820143 |

Agenda:

| Sr. | Topic | Time | Who |
| --- | --- | --- | --- |
| 1. | Self-Introduction | 5 min | All Participants |
| 2. | Review action points from previous meeting minutes | 5 min | Kris |
| 3. | Update on WASH Hygiene Kit Strategy | 15 min | All Participants |
| 4. | Update on WASH Situation Analysis (qualitative inputs from WASH partners) | 20 min | All Participants |
| 5. | Introduction for HARP/WASH and assignment | 20 min | SI/ DEFID |
| 6. | Update from meeting with DC/TA on WASH issues and CMC issues in Sittwe | 15 min | All Participants |
| 7. | Update from NRS | 10 min | All Participants |
| 8 | AOB | 30 min | All Participants |

Minutes:

| Topic 1: Review action points from previous meeting minutes |  |
| --- | --- |
| Summary of discussion | - To discuss the WASH situation analysis especially how we can develop the quantitative & qualitative analysis on the WASH sector. There was a discussion about this issue within WASH Cluster last week and WASH Cluster is waiting the updates on the general situations of the camps from each agencies. Some agencies have already shared the updates. Once the WASH Cluster has received all the updates from all agencies, WASH Cluster will compile all and will share again to the agencies. On the qualitative data, we found that some of the data from some camps are still missing and WASH Cluster IM will try to put it in the database. So Nyi Nyi Thit will contact to the agencies to get some feedbacks and updates as necessary. - SOP Communication Strategy – there was a lot of discussion within WASH Cluster and agreed to remove some few words especially on the camp based staff or the service providers to construct infrastructures. We removed this article from the WASH communication strategy. - Latrine construction in Dar Pai camp – WASH Cluster tried to discuss with the RSG but they are busy with the vice president’s visit and WASH Cluster cannot meet with both DC and TA in Sittwe. WASH Cluster and MAUK also discussed about this overlapping issue of latrine construction in the camps. WASH Cluster will also discuss with the government to get some areas for the MAUK where has still gap. - Solar lighting issue – WASH Cluster raised this issue in the Protection Cluster and they have also planned to send some people from the Protection Cluster to attend the WASH Cluster meeting for the discussion of this solar lighting issue in Pauk Taw. But the responsible person from Protection Cluster is in Maung Daw and it is not possible to discuss this issue in this meeting. - TWG on HK – received many feedbacks from DRC on the HK strategy. Almost finished the PDM questions and the agencies can have access on google drive. - NRS issue – although the military operation is stopped, the access is still a problem. In term of WASH reporting mechanism, WASH Cluster tried to update the WASH data and shared the NFI/ WASH distribution tracking sheet to the agencies few days ago. - Review on the WASH Cluster workshop – WASH Cluster shared the WASH SOF to the WASH agencies last few days ago. Once the WASH Cluster has received the feedbacks from the agencies, the final version of the SOF will be shared to the WASH Cluster mailing list. |
| Action plan | - Waiting the updates from the WASH agencies for the general situation in their camps. Some have already provided, WC is waiting the updates - WC to share the final document of the WASH communication strategy. - WC to discuss with government to get the implementing areas for the MAUK. - WASH partners to review the meeting minutes from the WASH Cluster SOF workshop and send the feedbacks to Kris if there is any issue. |
| Topic 2: Update on WASH Hygiene Kit Strategy |  |
| Summary of discussion | - WASH Cluster has already shared the latest document with the comments from DRC. - There are two formats for the HK strategy; one is two be done every two months and the other is to be done every 6 months. These documents are in translation process and it will be in KOBO form. We can also do survey and training on KOBO. - Oxfam – We have been doing the PDM every 2 months and every after distribution. What are the key findings that we got from PDM and how are things to be improved? Haven’t seen any changes in term of distribution strategy and kits that we got feedbacks from the PDM. - WC- that’s also an expectation from the donors. - SCI – NRC is distributing some soaps in the camps for the camp cleaning campaign. SCI discussed with NRC manager and they will negotiate with the SCI WASH team before implementing the activities and will reduce the distribution. |
| Action Plan | - HK TWiG to continue the next discussion on the detail of focus group discussion for PDM monitoring |
| Topic 3: Update on WASH Situation Analysis (qualitative inputs from WASH partners) |  |
| Summary of discussion | - Received some few updates from some agencies. Not yet received from all agencies and still missing reports from CDN. |
| Action Plan | - The agencies which have not been sent the updates on WASH situation analysis to send to WASH Cluster. |
| Topic 4. Introduction for HARP/WASH and assignment |  |
| Summary of discussion | - HARP is the functioning part of DFID. In the process, they are looking at the changing from the consortium. The main work of the HARP includes to look at consortium what is happening, to improve the quality of work and to monitor the technical aspect of the service provided to the beneficiaries. HARP will be based in Sittwe near the SI office. |
| Action Plan | - WASH agencies to facilitate and support HARF facility in the process |
| Topic 5: Update from meeting with DC/TA on WASH issues and CMC issues in Sittwe |  |
| Summary Discussion | - Last week, WASH Cluster had a lot of inputs and notification from agencies. SCI (OTG_N), Oxfam (STMG), land compensation issue in Pauk Taw camp. - Oxfam stopped the activities in Say Tha Ma Gyi camp because CMC asked them to stop. - During the ICCG, WASH Cluster also proposed to OCHA about that issue. - Oxfam – there are 2 points from CMC why they stopped the Oxfam’s activities; the first one is the CMC don’t get the contract from Oxfam and the second one is they are not always been informed about the activities and the progress of the project by the Oxfam. CMC have never seen the SOP and they don’t have clear understanding on the part of selecting contractors. Only well understand between the organizations. So WASH Cluster should coordinate with the CCCM Cluster for the explanation and dissemination of SOP to the CMC members. - WASH Cluster and CCCM cluster also discussed about the salary to be paid to the CMC. |
| Action Points | - CCCM cluster to follow up with CCCM Cluster Co., and the government officials on the dissemination of SOP issue to the CMC. |
| Topic 6: Update from NRS |  |
| Summary Discussion | - The government said that the military operation is stopped. - WASH HK distributed conducted by some WASH agencies, such as Malteser/Mercy Malaysia, and UNICEF |
| Action Points | - Possible duplication of WASH supplies and NFI kits; WASH Cluster to follow up - WASH cluster to gather data on WASH support and response. |
| Topic 7: AOB |  |
| Summary Discussion | - DRC - Land owners in OTG South and North are interrupting. - WC – if any issue concerning with land owner issue, can approach to WC and can get to DC. - SCI – DRD implemented the one big drainage in the Basara. If we have some gaps, we can propose to the DRD if they have funding, they can implement. - SCI – Sept 2017 will manage the tracking of waste management to the desludging site. |
| Action Points | - CCCM and WASH Cluster to share the update contact list of government State focal points. |