Rakhine WASH Cluster

MoM Rakhine WASH Cluster Meeting

Date:   	21/10/2016

Venue: 	UNICEF

Time: 	2.00 Pm to 3:00 Pm

Chair: 	Rakhine WASH cluster coordinator

Attendees:

| No | Name | Designation | Organisation | Email | Phone |
| --- | --- | --- | --- | --- | --- |
| 1 | Aung Myo Min | WASH PC | SCI | Aungmyo.min@savethechildren.org | 09-250 598175 |
| 2 | Sandi Hla Htway | Administrator | BAJ | Sandihlahtwe123@gmail.com | 09-250 331606 |
| 3 | Anna MARIA | WASH PM | RI | anna.trzcinska@ri.org | 09-4583 71388 |
| 4 | Zaw Min Tun | WASH Team Leader | CDN | zawmintununhabitat@gmail.com | 09-250 591043 |
| 5 | John KNIGHT | WASH Co | Oxfam | jkinght@oxfam.org.uk | 09-4200 16876 |
| 6 | Stephanie Tam | WASH Co | DRC | stephanie.tam@drcmm.org | 09-451978852 |
| 7 | Walter Abelenda | WASH Manager | Malteser | walter.abelenda@malteser-international.org | - |
| 8 | Steph Matti | JIPS Co | DRC | Stephaie.matti@drcmm.org |  |
| 9 | Kyaw Swar Oo | WASH PM | MHDO | Kyawswaroo.ark@gmail.com | 09-2541 69057 |
| 10 | Saw Tun Naing | Field Assistant | MHDO | sawtunnaing@gmail.com | 09-451 208499 |
| 11 | Kyaw Thet | WASH Officer | UNICEF | kthet@unicef.org | 09-420731457 |
| 12 | Brice | WASH PM | SI |  | 09-420070354 |
| 13 | Lae Yee Win | WASH Officer | UNICEF | laewin@unicef.org |  |
| 14 | Kris | WASH Specialist | UNICEF |  | 09251104394 |

Agenda:

| Sr. | Topic | Who |
| --- | --- | --- |
|  | Introduction | All participants |
|  | Review the minutes of meeting from previous cluster meeting | All participants |
|  | Update on the GHD 2016 celebration | All participants |
|  | Update on RSG’s SOP guidelines to work in the camp | All participants |
|  | Update on WASH Technical Working Group on Hygiene Kits Strategy | All participants |
|  | Current situation in NRS | All participants |
|  | JIPS profiling, current progress and update | DRC |
|  | Coordination on Desludging activity | SI |
|  | Dry season contingency plan | WASH Cluster/Unicef |
|  | So Ro Ja Camp-Water Supply | UNICEF & Oxfam |

Minutes:

| Topic 1: Update on the GHD 2016 celebration |
| --- |
| Summary Update | Global Handwashing Day 2016 was celebrated both inside the camp in Sittwe and Pauktaw; and outside the camp such as in Mrak-U, Ponnagyon, Kyaktaw, and Sittwe. Solidarites International, camp management agencies such as DRC/LWF, UNICEF, Oxfam, and Save the Children celebrated the Global Handwashing Day event In total over 3391 female student, 4190 male student and in total 8081 student participated in the global handwashing day celebration 2016. |
| Action Points | WASH Cluster to share the GHD report to the Rakhine State Government |
| Topic 2: Update on RSG’s SOP guidelines to work in the camp |
| Summary Update | The draft of WASH Cluster letter to the State Secretary/GAD was drafted by WASH Cluster Coordinator. Feedback and comment were received by the WASH Cluster Coordinator regarding some issues as follows: a). One government agency to coordinate the joint assessment and monitoring, instead of 5 government agencies. 2 weeks period of notice, without any response it will be considered as an approval by the WASH Cluster b). WASH Cluster is promoting inclusiveness of the WASH programme, including selection of contractor which should be based on internal policy of each agency. c). Worker selection based on the independent technical selection of WASH agency. d). Land compensation is the responsibility of RSG; it could be made only under the approval of RSG. |
| Action Points | a). WASH Cluster to scan and share the two moslem contractor and share it to the cluster b). The draft of the letter will be translated into Myanmar Language and it will be delivered to State Secretary next week. |
| Topic 3: Update on the revision of WASH HK Strategy |
| Summary Discussion | a). DRD coordinated the work to revise the existing WASH HK Strategy. So far two coordination meeting/technical working group meeting were done. The WASH TWG attended by Oxfam, DRC, SI, and Save the Children; the four major WASH agencies who are working to distribute Hygiene Kits in the camp. b). Standardize PDM is being developed by the WASH TWG, progress will be shared to the WASH Cluster. c). CCCM/NFI Cluster is also working to develop similar strategy, as well as to assess the needs of the IDP. They are working to review the content of NFI kits. |
| Action Points | a). Kris to follow up with National Cluster Co. regarding the selection of consultant/NGO to carry on the work on market assessment at national scale level. b). The recommendation to revise the existing WASH HK Strategy will be based on the recommendation from WASH Cluster in Rakhine which is currently under development. c). WASH Cluster to share the existing Hygiene Kits Strategy, as well as to share the final document on the WASH TWG on Hygiene Kits strategy. |
| Topic 4: Current Situation in NRS |
| Summary Discussion | a). The last update from WASH Cluster meeting regarding the number of assistance given to the affected population, and the rejection from the local community to receive aids provided by UN/INGO. b). Feedback on the consolidated contingency plan for NRS was drafted and shared to the WASH cluster. b). Some progress regarding the current situation in NRS was provided by ACF via email. While access to NRS is the main challenge. At this moment, there are only Malteser, ACF, and CARE international who are presents in NRS, but none of these agencies could access NRS due to the TA issues. c). Malterser/Walter provided some update regarding the current displacement, about 80.000 displacement, equal to 16.000 HH until 20.000 HH in NRS and the main challenge to access NRS. |
| Action Points | a). WASH Cluster to have preparedness for at least 20.000 families; while the existing capacity is only for 2000 families. Prepositioning should be made based on the tentative figure shared by Malteser. b). All WASH agencies who are willing to work or ready to address the needs in NRS should coordinate with the WASH Cluster. Considering the big number of possible displacement, more agencies are welcome. c). UNICEF is planning to meet MRCS to discuss possible cooperation to response the needs in NRS, considering the rejection from the community to work with INGO/NGO & UN agencies. |
| Topic 5: JIPS profiling |
| Summary Discussion | a). JIPS is working to develop enumerated procedure to carry out the profiling study in the camp. b). Operational strategy to develop the JIPS is being carried out, so far there is no approval from the government. |
| Action Points | a). WASH Cluster to coordinate with JIPS on the profiling strategy of the IDP camp. |
| Topic 6. Dry season Planning |
| Summary Discussion | As now we are entering dry season period, WASH agencies are expected to have better preparedness this year. WASH Cluster via UNICEF, is available for potential dry season response and there is budget available. |
| Action Points | WASH agencies to submit/prepare dry season response plan; such as preparation for water boating. |
| Topic 7. Desludging Activity |
| Summary Discussion | DFID WASH consortium is now entering new phase of the proposal, probably there will be less money available to implement the liquid waste management activity. In the operation of STS/desludging work, especially collection of liquid waste DRC/CDN is required to put some liquid waste management activities into their internal budget, so that it could support the liquid waste management activity. |
| Action points | WASH Agencies are expected to put specific budget for Liquid Waste Management so that it could contribute to the DFID WASH Consortium |
| Topic 8. Sarojo Water Supply |
| Summary Discussion | There is a request from DRD to UNICEF; DRD is looking forward to replace the existing water supply system from Fuel water pumps, into electric water pumps. Oxfam handed over the facility to DRD nearly a year a go; and UNICEF is to confirm with Oxfam regarding the current programme and activity in Sarajo Camp so that assistance could be given to DRD |
| Action Point. | UNICEF to work with DRD to improve the water supply system for Sarajo Camp. |