Rakhine WASH Cluster

MoM Rakhine WASH Cluster Meeting

Date:   	24/06/2016

Venue: UNICEF

Time: 	10.00 – 11.30 AM

Chair: 	KRIS CAHYANTO, WASH Specialist & Rakhine WASH cluster

Attendees:

| No | Name | Designation | Organization | Email Address | Contact Phone Number |
| --- | --- | --- | --- | --- | --- |
| 1 | Zin Nyo Win | WASH Facilitator | CDN | mizin1325@gmail.com | 09 250451009 |
| 2 | Htwe Sein Hla | WASH Facilitator | CDN |  | 09 26304506 |
| 3 | Stephanie Tam | WASH Coordinator | DRC | stephanie.tam@drcmm.org | 09 451978852 |
| 4 | John Knight | PHE Coordinator | Oxfam | jknight1@oxfam.org.uk | 09 420016876 |
| 5 | Karine LACROIX | WASH PM Pauktaw | SI | rks.eme.pm@solidarites-myanmar.org | 09 42 175 15 54 |
| 6 | Nyein Chan | Monitoring Officer | SI | rks.mne.off@solidarites-myanmar.org |  |
| 7 | Nay Kan Moo | HP Activity Manager | SI |  | 09 452208830 |
| 8 | Lei Yee Nway | WASH Officer | UNICEF | lnway@unicef.org | 09 450015864 |
| 9 | Lae Yee Win | WASH Officer | UNICEF | Laewin@unicef.org | 09 254820143 |
| 10 | Han Min Htet | WASH Coordinator | SCI | hanmin.htet@savethe children.org | 09 440224018 |
| 11 | Myo Myint | WASH PO | PLAN | myo.myint@plan-international.org | 09 421721513 |
| 12 | Thaw Si Htin Zaw | WASH Acting PM | SCI | thawsihtin.zaw@savethechildren.org | 09 263358311 |
| 13 | Kyaw Thet | WASH Officer | UNICEF | kthet@unicef.org | 09 420731457 |

Agenda:

| Sr. | Topic | Who |
| --- | --- | --- |
| 1 | Self-Introduction | All Participants |
| 2 | Agenda introduction by Wash Cluster Coordinator | WASH Cluster Coordinator |
| 3 | Review of the previous WASH cluster meeting | WASH Cluster Coordinator |
| 4 | Update of activities per agency | All Participants |
| 5 | Flood Response | All |
| 6 | Emergency preparedness activities | All |
| 7 | Water Quality Monitoring | All |
| 8 | WASH Condition in Camps | All |
| 9 | New 4Ws matrix and reporting mechanism | WASH Cluster Coordinator |
| 10 | TOR for WASH Evaluator | CDN |
| 11 | AOB |  |

Introduction

- Self –Introduction by 13 people from 7 agencies attended the WASH coordination Meeting.

Minutes:

| Topic 4: Action points from update of activities by Agency |  |
| --- | --- |
| Update situation in targeted areas | DRC: DRC completed the hygiene kit distribution. The hygiene kit distribution is done in every two months, consist of laundry soap, bathing soap, sanitary pad, tooth paste, tooth brush, and shampoo. UNICEF: UNICEF reported that during the past few months, UNICEF through DRD worked to refill the dried 122 water ponds in 91 villages. Nearly 15.000 to 17.000 water container was distributed during that period, including the provision of fuel for the water boating. Save the children: Installation of Bio sand filter for latrine construction is ongoing in Thet Kal Pyin and Maw Thi Nyar Camps and regular hygiene promotion sessions and hygiene kit distribution in Camps and Villages (2 villages in Sittwe and 3 villages in Pauktaw). Tet Lan Project is implementing for livelihood and Infrastructure development activities in 64 villages in Pauktaw and Myebon townships by IRC & SCI together. CDN: latrine renovation is ongoing in Khaung Toke Khar and Ohn Daw Chay Camps and regular hygiene kit distribution is starting in their focal camps. Plan International: Regular hygiene promotion sessions and O & M training is conducted in some villages and relocated villages in Minbya township. Solidarities International: The situation in ANY village is getting worse. SI reported nearly 2000 people displaced from the camp, due to the ongoing conflict between new CMC member and old CMC member in the camp. It was reported about a half of the camp population have left the camps and move to the host communities. There was no response of causalities and there is no information about urgent needs for WASH during the displacement of IDP. Oxfam GB: Oxfam is starting to end the work of the latrine cleaner and gave the work to the community member. Ceramic Water filters post assessment is ongoing and planned to distribute the spare parts and replacement of ceramic filters if needed. |
| Action points | - DRC: Post distribution monitoring for WASH Hygiene Kits to be developed. At this moment DRC, SC, SI (Consortium) is using KOBO app to conduct the PDM. Post hygiène kits distribution (PDM) report and kits - SI: WASH Cluster to follow up the issue with the protection working cluster and CCCM cluster and Protection Cluster on the ongoing CMC issues in ANY village. - Oxfam: UNICEF and Oxfam meeting to meet the GAD or TA to solve some WASH issue in the camp. |
| Topic 5: Action Points from Flood Response |  |
| Update from emergency response | - Kyauk Khaung Village Tract, Thar Yar Gone Village in Minbya Township were hit by tornado on 9th June. Approximately 200 households were affected. 54 houses were reported heavily affected by the tornado and 6 of the houses were completely destroyed. Under the request from DRD, UNICEF provided 102 pcs of tarpaulins, rope, and 34 hygiene kits for the affected population. - Due to the torrential rain event starting from 9th until 13th June 2016, flash flood occurred in Thandwe. It was reported that 210 houses were completely destroyed in 12 villages, about 829 population were affected. In addition, 2 villages, Pa Rit & Yae Kauk, were heavily affected. UNICEF WASH team together with UNHCR provided rapid emergency response to the flood affected area in Thandwe. In total, 210 hygiene kits and 200 boxes of water purification P & G Sachet were distributed for 210 families in these 12 villages. - Due to the tornado event in 24 April 2016 in Mrauk-U, UNICEF provided 54 tarpaulins and ropes for the 43 affected households under the partnerships with local government, in particular DRD. |
| Action points | - Preparedness for more response during the rainy seasons. |
| Topic 6: Action Points from Emergency preparedness activities |  |
| Update from emergency preparedness plan | - OCHA is asking all clusters to draft the Humanitarian Response Plan for Rakhine State. This document will be used to guide the humanitarian response during emergency. - It is expected that the clusters are ready with approximately 10.000 caseload during emergency. It is important to have preparedness measure in place, in particular for WASH material. |
| Action points | - List of existing material available in Sittwe from all agencies. Most of the agencies does not have emergency WASH material for emergency preparedness and response. No aqua-tab available in Sittwe, however there are huge quantity of PUR sachets and Chlorine buckets within the UNICEF warehouse. Partners who need some PUR should contact UNICEF focal points. |
| Topic 7: Action Points from Water Quality Monitoring |  |
|  | - SI + SCI + Oxfam ( DIFID Consortium) conducted water quality testing is ongoing in the camps - DRD requested to WASH Cluster to test the arsenic testing of the water sample from Kyaung Gyi Lan and Min Gan Quarters, Sittwe |
| Action points | - WASH Cluster will share national guide line for water quality standard - Technical Working Group for WQT will be conducted. - SI + SCI + Oxfam ( DIFID Consortium) will be share the WQT result to WASH Cluster |
| Topic 8: Action Points from WASH Condition in Camps |  |
| Current situation in the camps | - Limitation of IEC material on WASH in The camp. So far there is no general WASH IEC material which can be used as a tool to deliver WASH hygiene education. Most of the agencies have their own IEC material. The IEC material developed by the government has less picture and contains a lot of information. |
| Action points | - Prior to the Global Hand Washing Day in 15.10.2016, it is recommended to have specific WASH technical working group to assess and review the existing IEC material. Other preparation for budgeting including prepositioning of material for GHD 2015 can be started within the next few months in the beginning of annual planning and should be included in the work plan. |
| Topic 9: Action Points from New 4Ws matrix and reporting mechanism |  |
| Feedback from last meetings | - So far only few agencies submitted the 4Ws matrix, namely Acted, SI and DRC. |
| Action points | - WASH Agencies need to send in time. |
| Topic 10: Action points from TOR for WASH Evaluator |  |
|  | - CDN shared the TOR to the WASH Cluster, however there was no presentation from CDN regarding the current progress of the consultation and report. |
| Action Point | - Next Cluster Meeting??? |
| Topic 11: AOB |  |
|  | Next meeting: Friday 8 July, 2016, 10:00 – 12:00, to be confirmed. |