Rakhine WASH Cluster

Agenda for Rakhine WASH Cluster Meeting

Date:   	29/03/2017

Venue: 	UNICEF office

Time: 	10:00h ~ 11.15

Duration: 	1.5 hrs

Chair:		Rakhine WASH Cluster

Attendees:

| No | Name | Designation | Organization | Email | Phone |
| --- | --- | --- | --- | --- | --- |
| 1 | Richard Tracey | Shelter/CCM/NFI | UNHCR | tracey@unhcr.org | 09 448027896 |
| 2 | Tito P. Revereal | PM | CDN | tito@cdnmyanmar.org |  |
| 3 | Dereje Deneke | WASH Snr. PM | SCI | Dereje.Deneke@savethechildren.org |  |
| 4 | Wint Wah Htay | WASH PC | SCI | wintwar.htay@savethechildren.org | 09422489527 |
| 5 | Nadine Eriksson | PC | Medair | pc-mmr@medair.org |  |
| 6 | Brice | WASH PM | SI | sit.watsan@solidarities-myanmar.org | 09-420070354 |
| 7 | Melvin Tebbutt | HARP | HARP | melvin.tebbutt@harpfacility.org | 09762492716 |
| 8 | Lae Yee Win | WO | UNICEF | laewin@unicef.org |  |
| 9 | Yvonne Muller | Engineer | ICRC | ymuller@icrc.org | 9 420 281 442 |
| 10 | Han Thein | R.P.C | MHAA | Hanthein.mhaa@gmail.com | 09 420117396 |
| 11 | Ewan Chainey | WASH Cluster Coordinator | Global WASHCluster | ebchainey@unicef.org | 09 423404899 |
| 12 | Aung Min Oo | WASH PM | RI | aung.minoo@ri.org | 09451978021 |
| 13 | Toe Toe Aung | PHE | Oxfam | Toetoeaung221175@gmail.com |  |
| 14 | Bagus | PHE | Oxfam | bgetyawan@oxfam.org.uk |  |
| 15 | Shalom | PO | Mercy Malaysia | shalom@mercy.org.my | 09451379743 |
| 16 | Wint Wah Htay | WASH PC | SCI | wintwar.htay@savethechildren.org | 09422489527 |
| 17 | Kris Cahyanto | WASH Specialist | UNICEF/ Cluster | bkcahyanto@unicef.org |  |
| 18 | Lei Yee Nway | WO | UNICEF | lnway@unicef.org |  |

Agenda:

| Sr. | Topic | Time | Who |
| --- | --- | --- | --- |
| 1. | Self-Introduction | 5 min | All Participants |
| 2. | Review action points from previous meeting minutes | 5 min | Kris |
| 3. | 4Ws Review | 15 min | Lae Yee |
| 4. | WASH Contingency Plan for 2017 OCHA | 5 min | Kris |
| 5. | Water Scarcity in Camp and rural Community | 10 min | Lae Yee |
| 6. | Update from NRS | 10 min | All Participants |
| 7. | Duplication of Health/NFI/WASH NFI | 10 min | Richard |
| 8 | Update on WASH Hygiene Kit Strategy TWG | 10 min | All Participants |
| 9 | Update on WASH Sitan | 10 min | All Participants |
| 10 | AOB |  | All Participants |

Minutes:

| Topic 1: Review action points from previous meeting minutes |
| --- |
| Summary of discussion | HK TWG to continue the next discussion on the detail of focus group discussion for PDM monitoring – Stephanie not present – follow up Revision on WASH 4Ws will be made to accommodate current WASH services in the camp – presentation alignment with consortium/HARP/Cluster WASH Cluster Officer will collect the data from WASH Agencies - ongoing HARP is compiling WASH activities in Camp for long term planning – update 07/04/17 GIZ: WASH Agencies who are interested to work on WASH/Nutrition development activities to contact GIZ – GIZ non - attendance/info/gap – follow up Hygien Kit/TWG will share two formats with COBO data base to WASH Cluster with English and Myanmar translation - ongoing SI won’t be responsible for current government latrine construction design, desludging and O&M in future in Dar Pai Camp. – need an update WASH Agencies will be compiling Training plan for 2017. |
| Action plan | HK TWG – No meeting since three weeks ago Data Collection for HK Assessment is done ( start Nov 2016 – finished Jan 2017); according the results, we need to change HHS economic situation and need to look for Health data Camp profiling Data will be covered for HHs Economic by UNHCR ( Advocacy Strategy stage) and data will be township level collection – DRC will finish camp profiling by end of May Next tender of shelter construction for Sin Tet Maw Camp, UNHCR will put bathing facilities slab in 77 Shelters – confirmation of this? |
| Topic 2: 4Ws Review |
| Summary of discussionto | WASH 4Ws review meeting was done on 24.03.2017 with 13 participants and discussed on small modification/adjustment to represent the existing situation in the camp One of the problem our 4Ws have no health relation show us what we should have indicators coverage. Current basic and assuming indicators are not correct. We need to go back to change so basic indicators are # of units each infrastructure items and in the points of Hygiene promotion. We should change calculation parts to be better. 4 W cannot be seen information and demonstration on representative % of functional how much we need to be covered. Need to be identify Gap and which we could find coverage and gap. For Hygiene Promotion; it was need on measuring behavior change and current one need to refine too heavy documents. Note: ongoing WASH Cluster coordinating with HARP on provision of revised 4ws incorporating the above – especially related to health indicators. |
| Action Plan | Revision on WASH 4Ws will be made to accommodate current WASH services in the camp and host villages/ surrounding areas. HHs & Population Data will be provided by CMAs New WASH Cluster Coordinator will follow up on 4 W update Current 4 Ws will be used for first Quarter 2017 and next quarter will be used with updated format Indicator will be calculated with Sphere Standard |
| Topic 3: WASH Contingency Plan for 2017 |
| Summary of discussion | WASH Agencies need to share their stock list and Contingency plan for 2017 – ongoing/not finalized Last ICCG Meeting, discussed on WASH Agency focal point for Township level and to prepare for Coordination Mechanism and Capacity Building with Local authorities and CBOs - ongoing |
| Action Plan | WASH Cluster will collect the data from WASH Agencies. ICRC support WASH facilities for Ah Htet Nan Yar Camp – possibility/Kris |
| Topic 4: Water Scarcity in Camp and rural Community |
| Summary of discussion | DRD is distributing water in water scarcity areas in 40 villages in 6 townships (Sittwe, Rathedaung, Mrauk U, Kyauktaw, Minbya and Thandwe Townships) with Rakhine State Government Fund and will be covered during April and in March could distributed in three townships – continue follow up information Cluster /UNICEF programme support. GAD requested WASH Cluster to support WASH Activities in some areas cannot be covered by Government – as above. |
| Action Plan | WASH Cluster will share water shortages villages and information about water shortage – after April |
| Topic 5: Update from NRS |
| Summary Discussion | No update – recent confirmation that RCO will be overall coordinator of the response? |
| Action Points | WASH Cluster will follow closely on this development |
| Summary Discussion | Some WASH items were distributed by CCCM partners in NRS; WASH Cluster would like to avoid and kind of overlapping and duplication of minimize some issues with Health Cluster If Non-WASH actors want to distribute any WASH items, they must need to report and share information before their plans to WASH Cluster WASH Agencies never received any information from NFI Cluster before by phone or massages or emails |
| Action Points | NFI Cluster coordinator will coordinate in future to avoid duplication between NFI Cluster and WASH Cluster in WASH related items distribution - Richard written an email to that end to all concerned. |
| Summary Discussion | No update |
| Action Points |  |
| Topic 8: AOB |
| Summary Discussion | Next WASH Cluster Meeting will be held on 07 April 2017. |
| Action Points | WASH Agencies will be compiling Training plan for 2017. |