Rakhine WASH Cluster

MoM Rakhine WASH Cluster Meeting

Date:   29/05/2015

Venue: UNICEF office

Time: 10:00h

Chair: National WASH Cluster coordinator (RWCC)

Attendees: SI, CDN, UNICEF, DRC, ACF, Oxfam, SCI, ICRC, OCHA,

Absentees:  RI

Agenda:

| Sr. | Topic | Time | Who |
| --- | --- | --- | --- |
|  | Self-Introduction & Agenda introduction | 5 min | All Participants |
|  | Positioning paper on Village relocation | 1 hour | All participants |
|  | Hygiene kit strategy progress toward 2015 Wash cluster Strategy definition | 20 min | All participants |
|  | EP&R inter-sectorial plan | 5 min | All participants |
|  | Wash in school emergency positioning notes | 10 min | All participants |
|  | Update H.E Working group | 10 min | All participants |
|  | Wash cluster strategy mid-term review | 10 min | All participants |
|  | AOB : - CWF update, - HWB update, - Village Working group | 10 min | All participants |

Minute:

| Introduction |  |
| --- | --- |
| Summary of discussion | Introduction of participants. OCHA special guest to present Village mapping product |
| Action Points |  |
| Topic 1 : Positioning paper on Village relocation |  |
| Summary of discussion | During the last Cluster meeting It was then agreed that an amendment of the wash cluster strategy (focusing on the maintenance and Operation in camps, and existing village approach) should be done with a position note defining specific assistance related to different scenario on “returns”. This operationalisation for each scenario should start including phasing out approach. However phasing out approach should be more globally endorsed within the HRP, taking again the centrality of protection in consideration. All participant agreed on the overall structure of document, and appreciated the principle definition, related to do no harm and centrality of protection. The scenario presented were accepted, but it was notice that some are missing. E.g a scenario about a camp morphing to a permanent location should be integrated. However it is also a very sensitive case scenario, while a differentiation should gave between a voluntary and acceptable morphing of a camp to a village sustainable living area, and an un-strategic participation to fix population in a location. This cannot be defined without the insight of protection sectors, to ensure we are really talking about ending displacement in an acceptable set up. It was questioned how to communicate the document to the government: So far the document aim to agree between wash actor, within the HRP, on the strategic orientation. While agree, best communication tools, maybe more operationalised will have to be developed toward authorities: So far the Shelter/Wash positioning note, translated in Myanmar and including sanitation component is the best document to be used. Exchanging on different case scenario, it appear some un-clarity on Pauktaw situation toward temporary shelter provided, leading to a settlement ion plot of origin or still in camp setting. Information to be cross check after the meeting with both DRC and SI, in the perspective also of the scenario definition. It was an opportunity for OCHA, to present a very interesting mapping exercise of locations affected (village and camps) showing micro socio-economic interaction at community level, geographically presented. It strongly recommended to Wash partner to liaise directly with OCHA either to develop our community understanding or feeding OCHA on the tools produced. Wash partner requested to have a little more time to send written comments on the document. NWCC insist on the importance of the document and now the need to partner to look closely on the package/indicator proposed per scenario. The document has been submitted to OCHA, Shelter and protection sector for any comment. |
| Action Points | - Propose a draft 2 in the coming 10 days - Continue to liaise such document with other sectors |
| Topic 2 : Hygiene kit strategy progress toward 2015 Wash cluster Strategy definition |  |
| Summary of discussion | ### The subject aimed to wrap up the progress on Hygiene kit switch of approach plan in the strategy, and to evaluate how collectively the approach should be adapted, and which can of modalities should be advice. (See below Wash cluster strategy extract) First at all was clarify that: - All agreed on the stopped for HK distribution in villages, which is not to be debated then - Nobody moved out of blanket distribution so far It is important then to differentiate, in camp, the strategic approach, globally the target, and the modality possible for distribution. On the strategic approach, the proposition to stop completely a Hygiene Kit distribution approach, to move only for an integrated incentive approach within hygiene education was rejected. The targeted approach on predefined criteria remain the orientation to be taken. Keeping however in mind that an overall strategic definition, should keep space for particularism per location (e.g. a very isolated camps, with strong restriction of mvt, and low access to market, could at some point be kept for a blanket distribution approach) All agreed that the criteria definition should be done in consideration of other cluster approach, and link with FS/livelihood development plan. Furthermore, it is about changing more globally the approach toward beneficiary, while other sectors also initiated changes: Those changes should be coordinated to avoid beneficiary confusion, stress, and even impacting their economic vulnerability… The changes of approach can take 3 month before being operationalised, especially to align all actors on common strategy and changing approach simultaneously. ### Market assessment are launch by DIFID consortium, and also other sectors, that should then orientate modalities: Cash, Voucher… DRC has also made a cash assessment related to wash, results to be share soon. ### Hygiene Kits (wash cluster strategy extract) In 2013 and 2014, the target population of hygiene kits has been the affected households in camps or villages – all IDP were entitled to a full hygiene kit every year and a monthly replenishment, hosting families as well. The refining of the hygiene kit strategy[1] collectively by all the partners, based on post-distribution monitoring results[2], and WASH agencies analysis, includes the definition of criteria for the population entitled to kits based on geographical context (per township) and based on vulnerability. In Sittwe Township, beneficiaries sell mainly the sanitary pads and the body soap in the markets in order to afford other services such as food items, medicine and education showing that the hygiene kits deserve rather a livelihoods aim than hygiene need. In 2015, the WASH Cluster collective decided to limit the hygiene kits distribution to IDP in camps only. An inter-sectorial coordination, in particular with NFI Cluster and Livelihoods working group, should be adopted, in particular related to a better understanding of the local market dynamics and the household basket share, and the feasibility of usage alternatives such as voucher systems will be explored. In other townships, although, there are examples of cases where all items distributed are used by the beneficiaries, the access to markets is variable and requires more detailed study. The lack of livelihoods opportunities for the IDP population leads to a dependency on WASH interventions as part of incoming generating activities: Hygiene kits are sold immediately in the markets, latrine cleaning as income. This dependency will not change unless other actors bring targeted livelihoods opportunities. |
| Action Points | - NWCC stimulate exchange on the subject with other sectors (NFI and FS cluster at least) - Diffusion of DRC and DIFID consortium study - Look at progress in 3 week during the Wash cluster strategic review planned |
| Topic 3 : EP&R inter-sectorial plan |  |
| Summary of discussion | OCHA published the first complete set of the ERPP plan. It include Rakhine contingency plan. Wash cluster plan is well documented, and not much feedback received by Rakhine partners. Document will be validated in coming week. |
| Action Points | - Last feedback to send in the coming week max |
| Topic 4 : Wash in school emergency positioning notes |  |
| Summary of discussion | A review of role and responsibility sharing for Wash in school approach in emergency has been formalize on a positioning note, following 2014 lesson learn. It define more space for education sector to intervene directly in facility development, while the sector have often funds opportunity for such purpose. The document highlight all risk and mitigation measure to avoid any confusion with Wash focal agency in place. Wash cluster partners validated the positioning paper, agreeing also that coordination should first at all strengthen at location level. |
| Action Points | - Receive last feedback from education sector for a final version (1 week max) |
| Topic 5 : Update H.E Working group |  |
| Summary of discussion | The technical HE WG has been well set up with already 2 meeting held. ToR and objectives were defined. Minutes has been produced for references. (attached below) The next meeting focus on hygiene promotion in education centers. Review of the TWG ToR’s Related to objective 1: Research on possible approaches in order to move forward from good knowledge of hygiene practices to actual behavior changes - Discuss ways to move forward on social marketing and participatory approaches - Discuss the need to have harmonized FGD tools/questions for social Related to objective 2: Develop practical hygiene promotion approach for education center (School, TLS, Youth center...) fitting in the education framework. - Oxfam to present school hygiene club strategy + discussions - Could UNICEF introduce/present 3 stars framework? + discussion - Invitation to Education actors and discussions around inclusion of hygiene promotion into education programs + discussions on coordination paper related to WASH in schools under discussion at cluster level, with emphasis only on the hygiene promotion aspects |
| Action Points | - Set up the TWG (SI & UNICEF) |
| Topic 7 : Wash cluster strategy mid-term review |  |
| Summary of discussion | All partner agree to have a full day workshop for a Wash cluster mid-term review, which will in the same time facilitate the interim HRP report to be produce in July. Tentative date 25 June to confirm In the meantime a Wash cluster meeting will be held the 12 June. |
| Action Points | - NWCC confirm date and propose agenda |
| Topic 8 : AOB and pending issue |  |
| Summary of discussion | - AWD response plan for Rakhine has been revised last month but still need to be consolidated and discussed further with the health cluster at Yangon level for some strategic positioning. Partner also mentioned to have an inclusion of nutrition cluster. - OFDA ToR for Ceramic filter analysis done, UNICEF to launch the advertisement - Latrine design for camp (semi-permanent) to be proposed updated - HWB project: Presne4tation of the tools done to Wash partner in a special session, last version data base awaited to launch data collection - Village working group: Better to stand by, waiting first for the finalization of the re-settlement positioning paper |
| Attachment |  |

[1] Hygiene kit strategy – WASH Cluster – under revision

[2] PDM Sittwe and Pauk Taw camps – SI August 2014, SCI September 2014, OXFAM September 2014SI October 2014