WASH Cluster Myanmar

Minutes of National WASH Cluster Meeting

Date: Tuesday 26th July 2016    Venue: UNICEF Meeting hall

Time: 2 -4pm

Chair: James Robertson, Interim WASH Cluster Coordinator

UN/NGO Participation: Trocaire, SI, SCI, OCHA, Oxfam, WHH, UN-Habitat, ACF (see attached participant list)

| Sr. | Topic | Time | Who |
| --- | --- | --- | --- |
| 1 | Self-Introduction | 5 min | All Participants |
| 2 | - Agenda introduction | - 5 min | James |
| 3 | - Review WASH HRP indicators and mid-year results (with specific focus on how new 4W monitoring impacts upon numbers) | - 1 hour | All Participants |
| 4 | - Confirm humanitarian WASH funding received for HRP actions. | - 10 min | All Participants |
| 5 | - Share key advocacy messages that WASH Cluster partners feel should be sent to the ICCG | - 20 min | All Participants |
| 6 | - AOB | - 5 Minutes | All participant |

Minute:

| Topic 1 : Agenda introduction by National Wash Cluster Coordinator |  |  |  |
| --- | --- | --- | --- |
| Summary of discussions |  |  | Brief introduction to the agenda of the meeting by James Robertson: - Agenda - a - Review and feedback on the new HRP indicators by the partners. b - Discussion of the preliminary mid-year results and their consequences for further planning of the humanitarian assistance. - Quick overview on humanitarian WASH funding received by the partners. - Discussion of key advocacy messages from the WASH Cluster to be transmitted to the ICCG. - Any other business. |
| Topic 2 : Review WASH HRP indicators (2a) and mid-year results (2b) |  |  |  |
| Summary of discussion | 2a. Review WASH HRP indicators Background on old indicators The previous 4W indicators were the result of a long process. New input variables were added and weighted according to what seemed most suitable at the time. While all of this additions were justified the result were highly complex indicators that required a lot of input variables (20 individual variables for 3 indicators). The complexity lead to a lack of transparency and made fast analysis difficult. Important aspects of new indicators The aim of the new HRP indicators is to keep the quality of the indicator high while limiting the number of input variables. WASH Cluster shared with the partners a preliminary dashboard that makes quick analysis possible. Data can be disaggregated by camp/village/host families/schools. This will in the medium to long term allow to better align and integrate partner and government strategies. The methodology of the proposed new indicators aims to include the multiple factors that make up a service. The focus should be as much on quantity as on quality and thereby give a more complete picture of service coverage. Hand in hand with the focus on quality goes a relative increase of the weight of operation and maintenance for the final indicator. This increased focus on operation and maintenance is important in the view of the protracted character of the humanitarian situation. Separate monitoring of operation and maintenance costs can further be expanded in the near future and is a first step to increase efficiency of service provision and decrease cost per beneficiary in the medium to long term. The calculation of the new HRP indicators (Water, Sanitation, and Hygiene) each comprises three sub-indicators/tests. These sub-tests aim to measure and balance qualitative and quantitative aspects of services provided to communities rather than individuals. The information for these indicators will be collected quarterly. Specific feedback on individual sub-tests: Water: Test 1: Ratio of functioning improved water points to people less than: 250 SCI With regard to functionality it was proposed that water flow rates could be taken into account to calculate the minimum acceptable amount of people per improved water source – as defined in the SPHERE standards. Test 2: HHWF coverage greater than: 80%. No comments. Test 3: Is regular water testing being undertaken: yes/no. It was highlighted by several partners that while the test asks for water testing it does not include the measures taken when the water source is found to be microbiologically or chemically unsafe. ACF: In Norther Rakhine State (NRS) ACF is currently mainly doing water testing. Actions taken after testing should also be reflected in the indicators. ACF proposes that partners can include comments/justifications when reporting numbers. WASH Cluster: Monitoring development projects in villages with the same indicators as projects in camps is challenging. Oxfam points out the difference of water quality at source versus at point-of-consumption due to recontamination through unsafe storage/handling at HH level. Ideally, water quality would be tested both at source and at point-of-consumption to get a more nuanced picture. However, for the HRP indicator this would overburden the partner’s testing capacity. The HRP indicator is limited to whether a water point is functional and safe or not. However, this important and highly relevant topic could be subject of a more in-depth study and safe water handling/storage at HH level should be included in hygiene promotion activities. Sanitation: Test 4: Ratio of functioning latrines to people less than: 20. SCI asks how a functioning latrine is defined. Does it include latrines that are full (“urgent need for desludging”) as long as they would be functional (intact superstructure etc.) when they would be desludged. Or, should only latrines be included that are actually being used at the time of assessment – thus excluding full latrines? Test 5: % of latrines requiring urgent desludging less than: 20%. It was discussed that the term “urgent desludging” is relatively unspecific. When is desludging “urgent”? One meter before the containment system fills up? Earlier in rainy season? Taking into account different designs etc. this leaves a lot of possibility for interpretation. ACF raises the point that the context between camp and non-camp locations is very different. In NRS most of the pits are abandoned when full and the superstructure reused for a new pit. Should desludging be taken into account when it is not practiced in scarcely populated rural settings where land availability is not a concern? ACF asks for guidance on how to deal with this situation in order to make the collected numbers more comparable between different partners and settings. WASH Cluster: The fact that indicators need to address both camps and non-camp locations makes more detailed definition necessary. In a more rural context desludging might not be necessary as long as the HH/communities have the means to close and rebuild their pit. This will need to be specified further. Test 6: Regular solid waste management undertaken: yes/no. Several partners ask for guidance on what is defined as “regular solid waste management”. Hygiene Test 7: Ratio of Hygiene promoters to people less than: 250. No comments. Test 8: % of HH with access to handwashing facility greater than: 40%. Oxfam: It needs to be specified what can be counted as a handwashing facility. Culturally buckets at the household level are sometimes preferred for handwashing than facilities close to the sanitation facility. This is a topic that seems very suitable to be further explores in the proposed KAP survey. Test 9: % of HH with access to soap greater than: 70%. ACF: A “Yes/No” – does the community camp/village as a whole have access to soap instead of percentages of the population – might be better suited for this indicator  Definition of key terms It was discussed that key terms used for the different tests need to be clearly defined and minimum requirements agreed upon in order to make the collected data comparable between different partners and geographical locations. As the indicators aim to assess and compare the situation in both camp and non-camp settings certain definitions/minimum requirements might be different depending on the location. (e.g. desludging vs. closure of pits)  KAP survey The three proposed indicators focus on service provision – accessibility, functionality and maintenance. In order to identify potential barriers to behaviour change/use of the provided services it is planned to conduct a KAP survey towards the end of 2016. A standardized questionnaire with 20 core questions for all WASH cluster members will be developed. To this core questions each cluster member can add question as per their (donor/context) needs. This will lead to a minimum common data set. SI proposes to help developing the minimum core questions based on KAP survey they recently conducted. KoBo Toolbox is recommended to be used for this survey by all partners. This will simplify collection and subsequent analysis of the data. The KAP survey needs to be funded by the partner’s own financial and personal resources. 2b. Discussion of the preliminary mid-year results and their consequences for further planning of the humanitarian assistance Results The new HRP indicators lead to a significant drop in apparent coverage reached in Q2 as new indicators focus more on functionality and quality of services rather than just basic coverage. The disaggregation of targets for camp beneficiaries and beneficiaries living outside of camps brings greater attention to disparities in services offered to those two groups. In camps an estimated 80% of the needs have been met whereas only an estimated 20% of the needs of the beneficiaries outside camps were met. It is suggested that this needs to be highlighted within HRP reporting Beneficiary data on WASH funds covering HRP beneficiaries in NRS (EC) have not yet been reported on (will follow shortly). Trocaire: Reporting challenges exist in Kachin, due to limited capacity of local partners. General considerations by UNICEF To meet obligations to the ICCG, OCHA has requested monitoring the three HRP WASH indicators only. However, the WASH cluster aims to be transparent on how we arrive at our reported numbers. E.g. Gender disaggregation is based upon proportionate split of estimated camp populations. WASH interventions target entire camp populations with due considerations of minimum commitments to safety and dignity of affected people. In view of the disparities of services offered to camp beneficiaries and non-camp beneficiaries several points were discussed/questions raised: Is it appropriate to assess the situation in camps and outside of camps under the same HRP targets? Should NRS be targeted under the HRP when main funding and approaches to programming are developmental in nature? Partners were clear about that there is currently more assistance in camps than outside camps both in Kachin/NSS and Rakhine. SI: When looking at the township level indicators in villages outside of camps (access to water and sanitation) “do-no-harm” and conflict sensitivity need to be flagged considering the disparities between camp/non-camp settings. Can a shift towards more development funding and a bigger participation of (local) government in rural WASH coordination be expected, and be the basis of a different approach to this discrepancy? WASH Cluster: Government is increasingly taking more ownership in managing both humanitarian and development work, but does seek partners to continue to work in camps. This will need to be considered for the next HRP. Partners: Currently, partners are not yet seeing evidence of new donor funding and are therefore forced to phase out projects in non-camp settings. There was a consensus that more investment outside of camps is needed. Further analysis using 2014 Census and DHS figures (final report expected for December 2016) should feed into advocacy messages to increase work in villages neighboring camps. Bigger question as to when humanitarian assistance stops and development begins especially in protracted humanitarian situations. |  |  |
| Action Points | - WASH Cluster will create a google doc for comments on HRP definitions (using as a basis that already suggested in the meeting). - Linked to this a glossary with definitions/minimum requirements for key terms will be prepared by UNICEF and shared with partners for review. - Commentary section will be added to enable non-camp partners to provide justification for achievements. - SI will prepare core KAP survey questions to be used by all WASH partners. |  |  |
| Topic 3 : Confirm humanitarian WASH funding received for HRP actions. |  |  |  |
| Summary of discussions | Was only discussed very briefly. WASH Cluster is following up on some specific omissions |  |  |
| Action Points | - WASH Cluster to follow up on specific cases and feedback to OCHA |  |  |
| Topic 4 : Key advocacy messages that WASH Cluster partners feel should be sent to the ICCG |  |  |  |
| Summary of discussion | WASH Cluster coordination team proposed that the HCT advocates for (A) greater transparency of sector/cluster economic inputs into IDP camps to better understand impacts of humanitarian intervention on local economies and (B) suggested a targeted multi-sectorial study to value combined inputs into IDP camps through food, NFIs, contracts, salaries & incentives. However, many partners felt that more transparency on economic inputs would yield big protection risks. Most of the partners disapproved of point A on this basis. After a discussion of the risks and benefits the following consensus was reached and put forward to the ICCG: The WASH cluster proposes a multi-sectorial study to better understand impacts of humanitarian intervention on local economies and better evaluate potentials to move to cash based intervention. |  |  |
| Action Point | - WASH Cluster will share the agreed upon advocacy message with ICCG. |  |  |
| Topic 6 : AOB |  |  |  |
| Summary of findings |  | - Roll-out of the 2015 IASC GBV Guidelines: Tentatively a visit to provide training for WASH Cluster partners is proposed for the 3rd week in September. - WASH monitoring by the government is starting, it will take time to improve quality of collected data due to HR, financial, and technical challenges. UNICEF supports this development in both humanitarian/preparedness and development related areas. - UNICEF has established a WASH roster forspeedy recruitment in emergencies and other consultancies. This advertisement will remain open until the end of the year: http://jobs.unicef.org/cw/en-us/job/495862 - Troicaire asked for the design of the semi-permanent latrines and bathing facilities to be shared on the MIMU google drive. - In view of the big improvements in internet accessibility over the past few months, more key documents will be uploaded on the WASH Cluster google drive: https://goo.gl/XSLk2B |  |
| Attachment: PRESENTATION attached |  |  |  |