## Slide 1: Learnings from Emergency WASH Response implementation __(MYANMAR)__
Asia Pacific Regional WASH humanitarian Learning Event
01-02 December 2014, Bangkok
Pullman hotel

## Slide 2: MYANMAR’s CRISIS profile
Cluster activated for 2 separate crisis:
  Rakhine State, inter-communal clash (June and october 2012)
  Kachin State, armed civil open conflict (Mid 2011 conflict broke out)
  Both leading to «IDP problematic», camps and villages need intervention
  Both crisis define «protracted» while IDPs are in camps between 2 to 5 years
  With potential clashes resurgence (with new IDP, and reduction of access)
  With environmental high risk in background (Cyclone, Storm, Flooding, earthquake) in Crisis Area (Rakhine) but also other potential states (ex: Delta)
In November 2012 Cluster HCT(re-)activated the health, shelter/NFI/CCCM, and WASH cluster for the Rakhine and Kachin emergencies
Wash cluster operational 1st january 2013

## Slide 3: MYANMAR’s CRISIS profile
Case load:
Rakhine:
  IDP in camps: 116,183 Persons
  IDP in Villages: 8,158
  Villager Crisis affected: 192,259
  Surrounding communities: 100,000
  Total: 416,600
  Total Wash cluster targeted 309,000
  Kachin:
  IDP in camps: 86,386 Persons
  IDP in Villages: 12,684
  Surrounding communities: 20,000
  Total: 119,801
  Total Wash cluster targeted 119,500
Notes: Explain:
Mention about South East not targeted by cluster, or more globally Humanitarian country plan
Surrounding community concept in a do no harm perspective + leading to different approach in villages
Explain NRS, which explained the differences in total target in Rakhine

## Slide 4: MYANMAR’s CRISIS profile
    Contextual constrainS:
    Kachin:
      State separated between GCA and NGCA, with difficult access to NGCA
      IDP camp spreAd in remote area
      Conflict resurgence (small scale emergency) leading to stand by
      Language barrier for Hygiene promotion
      Lack of governmental projection for relocation process vs durable solution
      Low Wash capacity of cluster members (Local NGO mainly)
    Rakhine
      Target population no recognized as neither as citizens nor as refugees
      Low Acceptance of International assistance by the local population
      Tensions between different ethnicities
      Strong control of action by Government/civil society
      Different agenda between humanitarian and politic
      Unadapted site selection in regards of Wash
Notes: Explain:
Mention about South East not targeted by cluster, or more globally Humanitarian country plan
Surrounding community concept in a do no harm perspective + leading to different approach in villages
Explain NRS, which explained the differences in total target in Rakhine

## Slide 5: WASH Emergency response strategy
Objectives defined for 2015, common for Kachin and rakhine
  People have equitable and sustainable access to sufficient quantity of safe drinking and domestic water
  people have equitable access to safe and sustainable sanitation and live in a non-contaminated environment
  people adopt basic personal and community hygiene practices
2015 plan financial request:
  Rakhine: 16.5 MUSD
  Kachin: 9.5 MUSD
Main activities
  Water points construction and rehabilitation
  Water Trucking/boating still needed
  Semi-permanent latrines construction and massive desludging
  Re-enforcement of self reliance of the community in a second phase
  Supply of NFI
  Village approach for water & sanitation based on a more community participation
  Hygiene promotion through outreach workers
  …
Notes: Explain:
  Slight limitation regarding Country humanitarian response plan applicable kind of all around the world…
  But supported by a necessary comprehensive and developed Wash cluster strategy, align with over response plan objective and figures
  Allowing stronger qualitative and quantitative indicator definition and then accountability, including practical technical and approach strategic orientation
  And leading to the development of appropriate IM tools
  Financial requirement more or less covered the past 2 years, but the needs remain stable (little decrease following hardware construction) due to: First phase of Emergency facility developed, switch to semi-permanent and probably switch to more durable solution, in addition to timely harmonization of proper standard
  Financial support for cluster structure coming form UNICEF wash fundings: very strong and appreciated support for structure set up and sharing ressources

## Slide 6: WASH Emergency Coordination capacity
Structure:
  National: 1 NWCC (FT UNICEF), and 1 national Information manager (Vacant)
  Rakhine: 1 Sub-cluster WC (TA UNICEF), 1 Monitoring and evaluation officer (stand by partner), 2 consultants, 4 national positions vacant since 8 months
  Kachin: 1 Sub-cluster WC (TA UNICEF) –double-hatting, 1 capacity building officer (stand by partners), 6 consultants
Coordination tools available:
  4W, extended to offer a global analysis oriented on beneficiary needs coverage, link with a Information management system (Snapshop, monthly report, systematic cross-analysis….)
  Including financial tracking
  Development of more qualitative Monitoring and evaluation tools, jointly done with partners and other coordination body (ex:CCCM), based on indicator declination targeting qualitative aspect
  Usual cluster meetings, re-enforced with Technical working group approach, and inters-sectorial coordination at all level
  Technical and approach guidance produced
  Training organized, with orientation with collective capacity shared
  Joint evaluation, or independent evaluation (possibly led by RECA – ex: Accountability study - )
  Strong link with donors (independently from UNCEF), and capacity to advice geographically, qualitatively and strategically
Notes:   Mention HR difficulties: Wish end of 2013 of the double hatting, and avoid double hatting position. But UNICEF recruitmet procedure not adapted for emergency in the context: Too slow both international and national, leading to lack of stability for proper development

## Slide 7: Cluster INITIATIVEs
Innovative approaches
  Collaboration with Hydrologist without Border (HWB)
  In-depth M&E tools under development
  Ceramic filter approach “pilot” under deployment as an alternative for water quality in protractile crisis: Evaluation necessary with OFDA
  Definition of “village” approach based on do no harm principle, linking LRRD
  Sludge management
  Wash in Nut need to be addressed
  Capacity building structure to enhance response by local partners
Unappropriated past approach:
  Bathing and hand washing due to space and cultural inadequate design
  Need to push for new technologies and knowledge for water (ex: Drilling…)
  Rain harvesting system
M&E learning:
  Needs important resources to reach objective cluster analysis
  Not easy to finance
  Balanced with collective approach and CCCM actors support
  Supported with OCHA/MIMU
  Necessary to have good leverage on actors
  Strongly expected from the donors
  To better influence strategic orientation
  Weakness to collaborate with Health cluster to tackle Wash impact on public health

## Slide 8: MAIN STRATEGIC CHALLENGEs
WATER: Improve water quality through upgrading of facilities and testing. Support maintenance through community-based groups and thereby empower beneficiaries. Develop alternative sources to cope with seasonal shortages. Expand, monitor and evaluate household solutions for water treatment.
Desludging operation coverage
HYGIENE: Hygiene promotion approach to be systematically developed in all locations. Reinforce social organization through outreach workers. Increase Cluster understanding about behaviour change drivers and barriers.
Increase Community self-reliance in camps
Ensure conflict sensitive approach through the coverage of villages with adapted approach
Increase geographical coverage and analysis of humanitarian (NRS)
Continue capacity building of local actors
Adapt technical approach to the protracted context with more durable definition
Coordinate with Authorities for a more joint leadership on Wash emergency

## Slide 9: Cause & effects analysis of key challenges faced during response phase
Coordination
Acceptance
Access
Political
Staffing
Gaps
Turn Over
Stable coordination
Site selection
Rainny season
Hydrogeology
Local capacity
Technical authorization
No national standards
Environment
Technical Capacity
Quality and timely response

## Slide 10: Cause & effects analysis for key Successes Set up during response phase
Strategic
Documented
Collective
Advocacy
Frequently Shared
Exploitable
Systematic
Standardized IM system
Prioritized
Pilot approach
Synergies
Harmonization
Collectively agreed
Formalised
Innovative
Standard definition
Improve beneficiary living conditions

## Slide 11: Learnings from Performance of Cluster during Response implemented
Learning on supporting Service Delivery
More stable structure should be deployed
Standardised basic IM tools to be put in place, which can evolve in the context
Partners knowlege on cluster mechanism to be increased at field level
Coordination cost mecahnism to be better pre-defined
Technical working group approach
Inter-sectorial coordination to enhance
Learning on Informing Strategic Decision Making
Information management is the key
Information sharing complex (partner assessment)
Complete wash cluster strategy aside HRP brings good value
External evaluation more systematic towards benefeciary perception
Advocacy capacity vs technical
Notes: WASH Emergency Response: Key Learnings & Goals Grid:
Which good practices should be preserved or developed?
Which practices should be avoided or eliminated?

## Slide 12: Learnings from Performance of Cluster on Response implementation
Learning on Planning & Strategy Development
If well planned, strong commitment of partners, re-enforcing collective spirit
Based on evidences, related to m&E tools
Learning on Advocacy
Dependant on synergy with other agencies as OCHA, HCT, inter-sectorial coordination
Need to better formalise Wash advocacy objectif and strategy

## Slide 13: Learnings from Performance of Cluster on Response implementation
Learning on Monitoring & Reporting
internal cluster HR ressources not easy to set up
Reporting against strategic plan in place
Cross cutting issue lightly measured, difficult to operationalize and priorize in the context for the partners, Cluster raise sensitisation constantly
Accountability evaluation done to be operationalized
Contingency Planning & Preparedness
Too approximative in absence of clear linkage with governement (under development)
Takled too quickly in the HCT agenda
Need linkage with other platforms as DRR

## Slide 14: Response SWOT analysis
What advantages do we have?
OPPORTUNITIES
M&E system in continuous progress
Inter-cluster re-enforcement (CCCM & Health)
National NGO capacity building
Regional Support (RECA + UNICEF REWS)
Lesson learn (Social mobilization & HP) and innovative approach
WEAKNESSES
Coordination with authorities (national level)
Difficulties to respond to water quality
HR Structure difficult to set up and unstable
Contingency and preparedness
THREATS
Humanitarian access & deviation of the aid
Protracted crisis
Lack of exit strategy and durable solution definition
Environmental hazard
STRENGTHS
Good set of actor on the field & LNGO active (Kachin)
Coordination tools in place, and Information management
TWG activated
External Recognition (Donors, OCHA, partners)
Notes: Can be changed into four separate slides covering one of the four topics highlighted: strengths, weaknesses, opportunities and threats to WASH programmes.

## Slide 15: Recommendations
The cluster should be perceived and explained as a project to be implemented with adequate means, financial, HR, tools,... While looking at its core objectives cannot be restricted in its definition just as a coordination tool.
One of The main components of the project should be based on precise situation analysis requiring more global investement in external evaluation
Then as a project should be evaluated, and the cost efficiency measured in order to balance the investment versus the added value to the benefiaries.