Standard Operating Procedures (SOPs)

for Service Providers constructing Infrastructure in IDP Camps

The following Standard Operating Procedures (SOPs) apply for the construction of all infrastructure in IDP camps e.g. Temporary shelters, health facilities, CCCM infrastructure, WASH facilities, education facilities, roads, bridges, culverts, drainage etc …

These Standard Operating Procedures apply to contracts over a threshold of $2,000. For minor works, where it may be difficult to identify professional contractors prepared to work in IDP camps, alternative modalities may be used. Suggestions for these modalities are provided after the primary modality.

| Topic | Standard Operating Procedure (SOP) |
| --- | --- |
| General | - In accordance with instructions from the RSG, all service providers must engage with the Camp Management Committees (CMCs) at all stages of project implementation. - Camp Management Agencies (CMAs) will facilitate the engagement of service providers with CMCs on request. - All service providers must coordinate closely with the relevant RSG Camp Focal Point, the Camp Management Agency (DRC, LWF or NRC) and the Camp Management Committee (CMC) throughout implementation. - Land compensation is the responsibility of the RSG. Service providers must NOT pay any compensation to landowners. Issues relating to land compensation should be referred to the GAD - Service providers should provide regular progress updates to the CMC in order for CMCs to report to the RSG Camp Focal Point. |
| Needs Assessments | - For transparency and accountability to both IDPs and the authorities, needs assessments should be conducted jointly with CMC members, community groups including women’s groups and youth groups and the appropriate RSG technical counterpart e.g. the Department for Rural Development (DRD) for WASH and shelter activities. - A copy of all needs assessments must be filed with the respective Camp Management Agency, CMC, RSG Camp Focal Point, TA, DC and respective Cluster/sector lead. |
| Approval for Construction | - Prior to construction, all service providers must seek formal written approval from the designated RSG Cluster/sector focal point. [This can be achieved at a Cluster/Sector level] - Service providers should consult with the Shelter Cluster prior to implementation for site planning purposes. - A joint site visit should be conducted before making a formal written request for approval. Participants for this site visit should include representatives from the Land Records Department (LRD), General Administration Department (GAD) and relevant RSG technical counterpart (usually the DRD) and CMC members. - Letters requesting approval for construction must include details of the outcome of the joint site visit mentioned above, the number and locations of the infrastructure as well as a design. Approval is granted by the RSG Cluster/Sector focal point. [Note that approval is usually granted at a project level rather than for individual structures] |

| Topic | Standard Operating Procedure (SOP) |
| --- | --- |
| Contracts | - Service providers must NOT directly contract Camp Management Committees (CMC) or camp-based staff of the service provider to construct infrastructure. - All construction contracts must be awarded to contractors registered with the RSG and approved to work in IDP camps. [The RSG list of approved contractors is available from DRD as well as the Shelter & WASH Clusters] - Construction contracts are awarded in accordance with the internal rules and regulations of the service provider |
| Labour | - Service providers must make every effort to ensure labour opportunities, both skilled and unskilled, are offered using a gender-balanced approach to IDPs living in the camp where implementation is occurring - Service providers must make every effort to ensure equal pay for women and men - In accordance with the National law, children must not be employed - To facilitate a transparent process of labour selection, Camp Management Agencies (CMAs) are responsible for supporting CMCs to compile lists of camp based labour; both skilled and unskilled. These lists should be posted on information boards and updated regularly. Complaints regarding inclusion or exclusion on these lists should be directed to the complaints desk of the relevant CMA - Whilst service providers are strongly recommended to ensure construction contracts include a clause demanding contractors maximize labour opportunities to IDPs, the final decision for the selection of labour rests with the contractor. |
| Field Based Problems | - Problems occurring in the field should be first reported to the Camp Management Agency, the CMC and the RSG Camp Focal Point or relevant RSG technical department. - If it is not possible to resolve problems in the field, they should be raised at the appropriate Cluster meeting by the service provider i.e. Issues relating to WASH activities should be reported to the WASH Cluster etc … - Issues relating to the misconduct of CMC members should be referred to the GAD by the service provider and relevant Cluster/sector coordinator |
| Completion of Infrastructure | - Ensuring the quality of construction is the responsibility of the service provider. - Final monitoring of construction should be conducted jointly by the service provider, CMCs, community groups including women’s groups and youth groups and the relevant RSG technical focal points. - The service provider is responsible for informing the Shelter Cluster of the completion of new infrastructure in order to update site plans. - The service provider is responsible for providing the RSG with a completion report of completed infrastructure. This is done at a project level and should include the number of structures constructed, locations of the structures, photographs of completed works and design drawings. - Service providers are advised to submit handover documents to the RSG following the completion of infrastructure projects. |

Work under a threshold of $2,000

For minor works, it may not be practical or even possible to identify a contractor willing to work in IDP camps with minimal profit. For this reason, where necessary, an alternative modality for minor works may be considered. Firstly, the modality should only be used for work under the threshold of $2,000.

| Topic | Standard Operating Procedure (SOP) |
| --- | --- |
| Condition | - Work must be of a value less than $2,000 |
| Contractor | - Partners can hire a local or camp-based company to complete the work. CMCs can be used to provide names of local contractors for camp-based works. |
| Labour | - As above |
| Field Based Problems | - As above |
| Completion of Infrastructure | - As above |