**PROTECTION MAINSTREAMING TRAINING PLAN**

A training plan was established to ensure that protection principles are mainstreamed throughout the response. The following activities will be organized between June and December 2017 by the Protection Mainstreaming Focal Points.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Location** | **Sector** | **Activity** | **Target** | **Target Audience** | **Timeline** |
| *Cluster/Sector Level* | | | | | |
| Yangon | WASH | Briefing Session on Protection Mainstreaming  (2 hours) | 1 session per cluster/sector | Cluster/Sector Meeting | June 2017 |
| Health |
| Education |
| CCCM |
| Food Security |
| Sittwe | CCCM/Shelter | Briefing Session on Protection Mainstreaming  (2 hours) | 1 session per cluster/sector | Cluster/Sector Meeting | June 2017 |
| Education |
| Food Security |
| Health |
| WASH |
| Myitkyina | CCCM/Shelter | Briefing Session on Protection Mainstreaming  (2 hours) | 1 session per cluster/sector | Cluster/Sector Meeting | Depending on cluster meeting schedule |
| WASH |
| Education |
| Health/Nutrition |
| Bahmo | All sectors | Briefing Session on Protection Mainstreaming  (2 hours) | 1 session | GMC Meeting | Depending on the GMC meeting schedule |
| Lasho | All sectors | Briefing Session on Protection Mainstreaming  (2 hours) | 1 session | GMC Meeting | Depending on the GMC meeting schedule |
| *Field Staff / Frontline Workers* | | | | | |
| Sittwe  (IDP Camps) | CCCM/Shelter | Training on Protection Mainstreaming | 1 session | Camp-based staff and CMC members | October 2017 |
| Sittwe | Education | Training on Protection Mainstreaming | 1 session | Teachers, school directors, parent/student-associations, project officers | July 2017 |
| Sittwe | Food Security | Training on Protection Mainstreaming | 1 session | Distribution officers, project officers | July 2017 |
| Sittwe | Health | Training on Protection Mainstreaming | 1 session | Health center directors, doctors, midwifes, health committees, | July 2017 |
| Sittwe | WASH | Training on Protection Mainstreaming | 1 session | Engineers, hygiene promotion officers, water and sanitation officers | First week of June |
| Mawydaw | All sectors | Training on Protection Mainstreaming | 1 session | Local NGOs staff | July 2017 |
| Bahmo | All sectors | Training on Protection Mainstreaming | 1 session | UNHCR implementing partners | To be determined |
| Laiza | All sectors | Training on Protection Mainstreaming organized by Metta | 1 session | Local NGOs staff | To be determined |

**Material Available**

The following material is available to conduct the briefing and training sessions:

* GPC Training Manual (English)
* PowerPoint Presentation for a Briefing Session of 2 hours for Cluster Leads and Members (English)
* PowerPoint Presentation for a Training Session of 4 hours for Field Staff and Frontline Workers (English)
* Brief on Protection Mainstreaming (English – Myanmar)
* Protection Mainstreaming Video (English – Myanmar)
* Sector-Specific Checklists for Rakhine and Kachin (English)
* Series of Exercises