Cross Line Mission report – WASH

Mai Ja Yang

31st March – 5th April 15

WASH Participants

Sai Han Lynn Aung (WASH cluster)

Agenda

| Day | Places | Activities |
| --- | --- | --- |
| 1st April 15 | Bahmo – Mai Ja Yang | Travelling |
| 2nd April 15 | Pa Ka Tawng, Dum Bum | HK distribution, monitoring WASH situation |
| 3rd April 15 | NHkawng Pa | monitoring WASH situation Meet with WPN, IRRC |
| 4th April 15 | Mai Ja Yang – Bahmo | Field visit of Htang Nya boarding house Travelling |

Main activities:

- HKs distribution

- Field visit monitoring in three camps and one boarding house

- Bilateral meetings with WASH focal agency and CCCN leader

- Discussion with IDPs

- Meeting about Htang Nya Boarding House  (See CP report)

Summary:

The basic WASH needs are ensured in the visited IDPs locations. The main reencountered issue is the overall quality of GFS design that leads to turbidity and to discontinuous water supply during rainy season. Besides, Operation and maintenance of WASH facilities need to be rationalized and optimized to secure the access to wash facilities. As in other areas of Kachin there is no specific appropriate excreta disposal site leading to increase risks for public health. HP activities are still needed and should be continued. Capacity development of local actors should be reinforced in order to improve the planning, monitoring and implementing of WASH actvities

4W extract before field visit

| Township | Site | HH | PP | Water coverage | CWF coverage | Latrine coverage | Bathing coverage | Hand washing coverage | HK/coverage | Social mobilization |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Momauk | Dum Bum | 116 | 602 | 100% | 0% | 100% | 66% | 100% | needed | Low results |
| Momauk | Pa Ka Tawng | 561 | 2457 | 100% | 50% | 100% | 32% | 100% | No need | Low results |
| Momauk | Nhkawng Pa | 369 | 1633 | 100% | 100% | 49% only for semi permanent | 35% | 59% | Need to check | Low results |

4W extract after field visit

| Township | Site | HH | PP | Water coverage | CWF coverage | Latrine coverage | Bathing coverage | Hand washing coverage | HK/coverage | Social mobilization |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Momauk | Dum Bum | 117 | 620 | 100% | 0% | 100% | 66% | 100% | 100 % coverage following HK distribution during the cross line missions | Low results |
| Momauk | Pa Ka Tawng | 561 | 2457 | 100% | 50% | 100% | 32% | 100% | No need | Low results |
| Momauk | Nhkawng Pa | 369 | 1633 | 100% | 100% | 49% | 35% | 59% | No need | Low results |

***yellow highlight means changes before and after cross line trip

Remark: Given the time constraint, it has been not possible to check all the WASH facilities and updated data have been provided by WPN team. The size of the IDPs locations and number of WASH facilities makes especially challenging the counting of WASH facilities during cross-line missions

WASH NFI distribution

| Hygiene items | Distributed items |
| --- | --- |
| Dum Bum Camp | 117 full hygiene kits have been distributed to all HHs of Dum Bum Camp (321 male and 299 female -620 people living in this camp) accompanied with awareness session to IDPs. A set of 30 poster (including diagram and transmission poster) have been distribute to CCCM. |
| Pa ka Tawng | A set of 30 poster (including diagram and transmission poster) have been distribute to CCCM. |
| Nhkawng Pa | A set of 210 poster (including diagram and transmission poster) have been distribute to CCCM |

WASH monitoring

WASH monitoring was carried out with the WASH field assistant of WPN through meeting with CCCM leader, and field observations

| Water | Main issues / Observations |
| --- | --- |
| Dum Bum Camp | Need to increase the number of tapstands form 4 to 6 in order decreasing queuing time for the main water storage tank. Turbidity issues during rainy season |
| Pa ka Tawng | The poor design of GFS led to turbidity issues during rainy season and to discontinuous water supply WPN technician is installing Bio Sand filter installation at water level (tap) (36 in PakaTawng) Need for water storage container at the school location to make water available for pupils. |
| Nhkawng Pa |  |

| Sanitation | Main issues / Observations |
| --- | --- |
| Dum Bum Camp | No specific issues |
| Pa ka Tawng | Desludging issues: 6 latrines need to desludged 10 emergency latrines need to be decommissioned |
| Nhkawng Pa | 30 emergency latrines need to be decommissioned WPN plan to build 20 semi permanent in April with SCI fund |

| HWTS | Main issues / Observations |
| --- | --- |
| Dum Bum Camp | There is a need for CWGF at household level |
| Pa ka Tawng | CWF from China have been distributed from Chinese religious institution two 2 years ago and most of them seems to be still functioning. Exact CWF was not known either by WPN staff nor CCCM but not all HHS own a CWF. |
| Nhkawng Pa |  |

| Operation and maintenance | Main issues / Observations |
| --- | --- |
| Dum Bum Camp | No specific issues |
| Pa ka Tawng | The use of GFS reduces running cost but maintenance of GFS is quite an issue. Need to rationalize maintenance. There are two technicians per IDP location for water maintenance |
| Nhkawng Pa |  |

| Hygiene | Main issues / Observations |
| --- | --- |
| Dum Bum Camp | The Hygiene promotion activities stopped at the end of 2014 but are still needed |
| Pa ka Tawng | Despite the presence of HP volunteers who carry out 15 HP sessions per month and the presence of WPN field assistant who undertake one HP session per month, there are still some room for hygiene improvement. Based on field observation, some latrines were not clean and the personal hygiene of some children would need to be improved. |
| Nhkawng Pa |  |

| Hygiene items | Main issues / Observations |
| --- | --- |
| Dum Bum Camp | IDPs didn’t received hygiene kit since more than 1 year due to: - Remote NGCA, - Gap funding from KMSS IDPs need to go to China to buy WASH NFI. The market is located one hour by walking and 15 mn by motorbike. The cash transfer program managed by KMSS is ending at the end of April and IDPs were using partially this cash to buy some WASH NFI. |
| Pa ka Tawng | No specific issues. IDPs receive WASH NFI from WPN with SCI funds |
| Nhkawng Pa |  |

Field visit in Htang Nya Boarding house

The below recommendations for WASH activities should be in line with CP guideline and criteria and no WASH interventions should be undertaken before prior coordination with CP sector and concerned actors. The situation of this boarding (possible relocation)  is under discussion with actors from different sectors / cluster

Sanitation facilities

Latrines

There are 6 emergencies and 3 permanent latrines, ie a total of 9 latrines. With a ratio of 50 student per latrines, the current sanitation facilities enables the sanitation access for 450 students. There are 163 student in this boarding houses meaning that there is a need for 4 latrines plus two for e teachers.

Action: The existing semi-permanent latrines need upgrading.

Hand washing

No hand washing stations

Action: construction of hand washing stations

Bathing facilities

There are 2 gender separated bathing spaces that seem enough (ratio of 100 student per bathing facility).

No need for action

Water

1 water storage tank supplied by 1 tube well

The school is connected to one GFS from the surrounding village but water availability depends on arrangement with villagers

Action: Finalize the pipe network and set up appropriate agreement with villagers for water use

The WASH situation has to be followed up according to CP issues

Main recommendations

- Plan a briefing with IRRC’ new secretary about WASH cluster mandat and functions

- To upgrade GFS design of Pa Ka Tawng, NHkawng Pa and Dum Bum

- Rationalize and optimize water management and monitoring in WPN IDP camps

- Need to follow up the final decision for Htan Nyar school and correlated WASH needs

- Train  WPN on SOP for desludging activities,

- Advocate for a small scale excreta as excreta are currently sent directly to river

- Based on field observation (not clean latrines, dirty children) and discussions with WPN staff, reinforce Hygiene promotion activities in Mai Ja Yang camps even if some people seem familiar with hand washing.

- Capacity development of WPN WASH staff for planning monitoring,

- Rationalize and monitor CWF (ceramic water filter) distribution in Mai Ja Yang area in order to have 100% coverage and undertake HP activities to ensure the proper use of these CWF,

- Follow up with KMSS for HP activities in Dum Bung camps

Prepared by: Sai Han Lynn Aung

WASH cluster Officer,

UNICEF, Myitkyina Office